## Outokumpu- S2P Project
Project Name | Project Category | Ancestors | Project Manager | Level | Phase/Milestone | At Risk? | Schedule Health | Task Name | Status | Start Date | End Date | % Complete | On Hold? | Not Applicable? | Duration | Predecessors | Description | Owner | OwnerShip | Priority | Total Float | Critical ? | Baseline Start | Baseline Finish | Variance | Status Comment | Area | Comments | Assigned To | Start | Finish | RAG
| #UNPARSEABLE | 0 | Aftab Hashambhai | 0 |  |  | Green | Zycus - Titan S2P Implementation | In Progress | 2025-12-05 | 2026-12-07 | 71% |  |  | 262d | [5 empty] | 0 | TRUE | 2026-05-03 | 2026-05-20 | -2d
| #UNPARSEABLE | 0 | Aftab Hashambhai | 0 |  |  | Yellow | Phase 1- S2C | In Progress | 2025-12-05 | 2026-07-14 | 92% |  |  | 158d | [5 empty] | 104 |  | 2025-12-05 | 2026-07-02 | -6d |  |  |  | abhilasha.s@zycus.com |  |  | Yellow
| #UNPARSEABLE | 1 | Aftab Hashambhai | 1 | Project Initiation |  | Green | Contract Sign Off | Completed | 2025-12-05 | 2025-12-05 | 100% |  |  | 1d | [5 empty] | 261 |  | 2025-12-05 | 2025-12-05 | 0 |  |  |  | abhilasha.s@zycus.com |  |  | Green
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Contract signing between Titan and Zycus | Completed | 2025-12-05 | 2025-12-05 | 100% |  |  | 1d | [5 empty] | 261 |  | 2025-12-05 | 2025-12-05 | 0 |  |  |  | Titan Project Sponsor, Zycus Sales |  |  | Green
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Contract Sign Off | Completed | 2025-12-05 | 2025-12-05 | 100% |  |  | 0 | [5 empty] | 262 |  | 2025-12-05 | 2025-12-05 | 0 | [6 empty] | Green
| #UNPARSEABLE | 1 | Aftab Hashambhai | 1 | Data Gathering |  | Green | Project Initiation and Data Gathering | Completed | 2025-12-15 | 2026-02-27 | 100% |  |  | 55d | [5 empty] | 201 |  | 2025-12-15 | 2026-02-27 | 0 |  |  |  | abhilasha.s@zycus.com |  |  | Green
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Project Kick Off | Completed | 2025-12-15 | 2026-02-06 | 100% |  |  | 40d | [5 empty] | 216 |  | 2025-12-15 | 2026-02-06 | 0 | [6 empty] | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Review Contract Scope | Completed | 2025-12-15 | 2025-12-15 | 100% |  |  | 1d | [5 empty] | 255 |  | 2025-12-15 | 2025-12-15 | 0 |  |  |  | Zycus Project Resources Manager |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Assign Project Team and Internal communication | Completed | 2025-12-19 | 2025-12-19 | 100% |  |  | 1d | [5 empty] | 251 |  | 2025-12-19 | 2025-12-19 | 0 |  |  |  | Zycus Project Resources Manager |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Zycus Project Team mobilization and Team alignment | Completed | 2025-12-19 | 2025-12-19 | 100% |  |  | 1d | [5 empty] | 251 |  | 2025-12-19 | 2025-12-19 | 0 |  |  |  | Zycus Project Resources Manager |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Setup Project [Server, Email alias, Internal Applications, Central Drive, Internal ticket for STAGING Set Up] | Completed | 2026-01-05 | 2026-01-05 | 100% |  |  | 1d | [5 empty] | 240 |  | 2026-01-05 | 2026-01-05 | 0 |  |  |  | Zycus Project Team |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Raise ticket for STAGING Set Up creation | Completed | 2026-01-05 | 2026-01-05 | 100% |  |  | 1d | [5 empty] | 240 |  | 2026-01-05 | 2026-01-05 | 0 |  |  |  | Zycus Product Specialist |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Sales / PreSales / Pilots handover | Completed | 2026-01-07 | 2026-01-07 | 100% |  |  | 1d | [5 empty] | 238 |  | 2026-01-07 | 2026-01-07 | 0 |  |  |  | Zycus Project Manager, Zycus Project Team, Zycus Sales |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Pre-kick off meeting with internal stakeholders | Completed | 2026-01-16 | 2026-01-16 | 100% |  |  | 1d | [5 empty] | 231 |  | 2026-01-16 | 2026-01-16 | 0 |  |  |  | Zycus Project Manager, Zycus Project Team, Zycus Sales |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Finalize kick off meeting schedule | Completed | 2026-01-16 | 2026-01-16 | 100% |  |  | 1d | [5 empty] | 231 |  | 2026-01-16 | 2026-01-16 | 0 |  |  |  | Titan Project Manager, Titan Project Sponsor, Zycus Sales |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Kick off meeting [Introduction Meeting] | Completed | 2026-01-20 | 2026-01-20 | 100% |  |  | 1d | [5 empty] | 229 |  | 2026-01-20 | 2026-01-20 | 0 |  |  |  | Titan Core Project Team, Titan Project Manager, Zycus Consultant, Zycus Product Specialist, Zycus Project Manager, Zycus Project Team |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Share Product specific templates [Questionnaire, Product specific Pre-Requisites, Workshop Agenda, User Details template] with Titan | Completed | 2026-02-02 | 2026-02-06 | 100% |  |  | 5d | [5 empty] | 216 |  | 2026-02-02 | 2026-02-06 | 0 |  |  |  | Zycus Product Specialist, Zycus Project Manager |  |  | Green
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Zycus Project Set-Up | Completed | 2026-01-26 | 2026-02-02 | 100% |  |  | 6d | [5 empty] | 220 |  | 2026-01-26 | 2026-02-02 | 0 | [6 empty] | Green
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Kick-off Meeting | Completed | 2026-01-20 | 2026-01-20 | 100% |  |  | 0 | [5 empty] | 230 |  | 2026-01-20 | 2026-01-20 | 0 | [6 empty] | Green
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Data gathering & pre-requisites complete. Ready for onsite workshop | Completed | 2026-02-02 | 2026-02-27 | 100% |  |  | 20d | [5 empty] | 201 |  | 2026-02-02 | 2026-02-27 | 0 | [6 empty] | Green
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Zycus BootCamp | Completed | 2026-01-27 | 2026-02-02 | 100% |  |  | 5d | [5 empty] | 220 |  | 2026-01-27 | 2026-02-02 | 0 | [6 empty] | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Intake with iSupplier | Completed | 2026-01-27 | 2026-01-27 | 100% |  |  | 1d | [5 empty] | 224 |  | 2026-01-27 | 2026-01-27 | 0 | [6 empty] | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | iRisk | Completed | 2026-01-27 | 2026-01-27 | 100% |  |  | 1d | [5 empty] | 224 |  | 2026-01-27 | 2026-01-27 | 0 | [6 empty] | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Intake with isource & ANA | Completed | 2026-01-28 | 2026-01-28 | 100% |  |  | 1d | [5 empty] | 223 |  | 2026-01-28 | 2026-01-28 | 0 | [6 empty] | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Intake with iContract | Completed | 2026-02-02 | 2026-02-02 | 100% |  |  | 1d | [5 empty] | 220 |  | 2026-02-02 | 2026-02-02 | 0 | [6 empty] | Green
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Pre-design workshop session for integration | Completed | 2026-02-06 | 2026-02-20 | 100% |  |  | 11d | [5 empty] | 206 |  | 2026-02-06 | 2026-02-20 | 0 | [6 empty] | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Pre design integration Sesion -isupplier | Completed | 2026-02-09 | 2026-02-10 | 100% |  |  | 2d | [5 empty] | 214 |  | 2026-02-09 | 2026-02-10 | 0 | [6 empty] | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Pre design integration Sesion -users | Completed | 2026-02-13 | 2026-02-13 | 100% |  |  | 1d | [5 empty] | 211 |  | 2026-02-13 | 2026-02-13 | 0 | [6 empty] | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Predesign integration session -iMaster | Completed | 2026-02-16 | 2026-02-16 | 100% |  |  | 1d | [5 empty] | 210 |  | 2026-02-16 | 2026-02-16 | 0 | [6 empty] | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Sample data collection | Completed | 2026-02-06 | 2026-02-06 | 100% |  |  | 1d | [5 empty] | 216 |  | 2026-02-06 | 2026-02-06 | 0 | [6 empty] | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Legacy data collection for supplier | Completed | 2026-02-06 | 2026-02-06 | 100% |  |  | 1d | [5 empty] | 216 |  | 2026-02-06 | 2026-02-06 | 0 | [6 empty] | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Legacy data collection for PO | Completed | 2026-02-06 | 2026-02-06 | 100% |  |  | 1d | [5 empty] | 216 |  | 2026-02-06 | 2026-02-06 | 0 | [6 empty] | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Legacy data collection for Contracts | Completed | 2026-02-06 | 2026-02-06 | 100% |  |  | 1d | [5 empty] | 216 |  | 2026-02-06 | 2026-02-06 | 0 | [6 empty] | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | System Setup Based on Samples | Completed | 2026-02-13 | 2026-02-20 | 100% |  |  | 6d | [5 empty] | 206 |  | 2026-02-13 | 2026-02-20 | 0 | [6 empty] | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Configure system using collected sample data. | Completed | 2026-02-13 | 2026-02-20 | 100% |  |  | 6d | [5 empty] | 206 |  | 2026-02-13 | 2026-02-20 | 0 | [6 empty] | Green
| #UNPARSEABLE | 1 | Aftab Hashambhai | 1 | Requirement Workshop |  | Green | Configuration Documentation Workshop | Completed | 2026-02-03 | 2026-03-20 | 100% |  |  | 34d | [5 empty] | 186 |  | 2026-02-03 | 2026-03-23 | 1d |  |  |  | abhilasha.s@zycus.com |  |  | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Configuration Documentation Workshop- Functional | Completed | 2026-02-03 | 2026-02-20 | 100% |  |  | 14d | [5 empty] | 206 |  | 2026-02-03 | 2026-03-13 | 15d |  |  |  | abhilasha.s@zycus.com |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | As-is Process walkthrough by Titan | Completed | 2026-02-03 | 2026-02-20 | 100% |  |  | 14d | [5 empty] | 206 |  | 2026-02-03 | 2026-02-20 | 0 | [6 empty] | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | iSupplier-As Is Process Discussion | Completed | 2026-02-03 | 2026-02-04 | 100% |  |  | 2d | [5 empty] | 218 |  | 2026-02-03 | 2026-02-04 | 0 | [6 empty] | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | iSource-As Is Process Discussion | Completed | 2026-02-13 | 2026-02-13 | 100% |  |  | 1d | [5 empty] | 211 |  | 2026-02-13 | 2026-02-13 | 0 | [6 empty] | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | iContract-As Is Process Discussion | Completed | 2026-02-17 | 2026-02-17 | 100% |  |  | 1d | [5 empty] | 209 |  | 2026-02-17 | 2026-02-17 | 0 | [6 empty] | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | iRequest-As Is Process Discussion | Completed | 2026-02-18 | 2026-02-18 | 100% |  |  | 1d | [5 empty] | 208 |  | 2026-02-18 | 2026-02-18 | 0 | [6 empty] | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | iRisk-As Is Process Discussion | Completed | 2026-02-19 | 2026-02-20 | 100% |  |  | 2d | [5 empty] | 206 |  | 2026-02-19 | 2026-02-20 | 0 | [6 empty] | Green
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Onsite- Design Session-Design Session Completion and Sign off | Completed | 2026-03-02 | 2026-03-20 | 100% |  |  | 15d | [5 empty] | 186 |  | 2026-03-02 | 2026-03-13 | 7d |  |  |  | abhilasha.s@zycus.com |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Workshop Kick-off & Introductions | Completed | 2026-03-02 | 2026-03-02 | 100% |  |  | 1d | [5 empty] | 200 |  | 2026-03-02 | 2026-03-02 | 0 | [6 empty] | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | iSupplier To-Be Process Design (Reg & Onboarding) | Completed | 2026-03-03 | 2026-03-03 | 100% |  |  | 1d | [5 empty] | 199 |  | 2026-03-03 | 2026-03-03 | 0 | [6 empty] | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | iSupplier To-Be Process Design (Data Mgmt & Perf) | Completed | 2026-03-04 | 2026-03-04 | 100% |  |  | 1d | [5 empty] | 198 |  | 2026-03-04 | 2026-03-04 | 0 | [6 empty] | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | iRisk-As Is Process Discussion | Completed | 2026-03-06 | 2026-03-06 | 100% |  |  | 1d | [5 empty] | 196 |  | 2026-03-06 | 2026-03-06 | 0 | [6 empty] | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | iSource-As Is Process Discussion & ANA functional Design and configuration Discussion | Completed | 2026-03-09 | 2026-03-09 | 100% |  |  | 1d | [5 empty] | 195 |  | 2026-03-09 | 2026-03-09 | 0 | [6 empty] | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | iContract-As Is Process Discussion & Intake with iContract functional Design and configuration | Completed | 2026-03-10 | 2026-03-10 | 100% |  |  | 1d | [5 empty] | 194 |  | 2026-03-10 | 2026-03-10 | 0 | [6 empty] | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | iRequest-As Is Process Discussion | Completed | 2026-03-11 | 2026-03-11 | 100% |  |  | 1d | [5 empty] | 193 |  | 2026-03-11 | 2026-03-11 | 0 | [6 empty] | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Consolidated review of proposed solution and "To-Be" design. | Completed | 2026-03-12 | 2026-03-12 | 100% |  |  | 1d | [5 empty] | 192 |  | 2026-03-12 | 2026-03-12 | 0 |  |  |  | abhilasha.s@zycus.com |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Review Risks, Assumptions, Issues, and Dependencies (RAID log),Next Steps | Completed | 2026-03-12 | 2026-03-12 | 100% |  |  | 1d | [5 empty] | 192 |  | 2026-03-12 | 2026-03-12 | 0 |  |  |  | abhilasha.s@zycus.com |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Legacy Migration Discussion and Approach | Completed | 2026-03-13 | 2026-03-13 | 100% |  |  | 1d | [5 empty] | 191 |  | 2026-03-13 | 2026-03-13 | 0 |  |  |  | abhilasha.s@zycus.com |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Go Value discussion & Project Plan | Completed | 2026-03-13 | 2026-03-20 | 100% |  |  | 6d | [5 empty] | 186 |  | 2026-03-13 | 2026-03-13 | -5d |  |  | Yet to recieve Sign off | abhilasha.s@zycus.com |  |  | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Draft IAD discussion & Sign off | Completed | 2026-03-12 | 2026-03-20 | 100% |  |  | 7d | [5 empty] | 186 |  | 2026-03-12 | 2026-03-12 | -6d |  |  | Yet to recieve Sign off | abhilasha.s@zycus.com |  |  | Green
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Integration Configuration Documentation Workshop | Completed | 2026-03-04 | 2026-03-05 | 100% |  |  | 2d | [5 empty] | 197 |  | 2026-03-04 | 2026-03-05 | 0 |  |  |  | Titan IT Project Manager, Titan Integration Team, Titan Project Manager, Zycus Integration Team, Zycus Project Manager |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | iSupplier outbound | Not Applicable | 2026-03-04 | 2026-03-05 | 100% |  | TRUE | 2d | [5 empty] | 197 |  | 2026-03-04 | 2026-03-05 | 0 | [6 empty] | Yellow
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | iSupplier Integration Overview | Not Applicable | 2026-03-04 | 2026-03-04 | 100% |  | TRUE | 1d | [5 empty] | 198 |  | 2026-03-04 | 2026-03-04 | 0 | [6 empty] | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | iSupplier Integration Scenarios and Mapping | Not Applicable | 2026-03-04 | 2026-03-04 | 100% |  | TRUE | 1d | [5 empty] | 198 |  | 2026-03-04 | 2026-03-04 | 0 |  |  | With OTK as of 23rd march |  |  |  | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | iSupplier Integration Mapping discussions | Not Applicable | 2026-03-04 | 2026-03-04 | 100% |  | TRUE | 1d | [5 empty] | 198 |  | 2026-03-04 | 2026-03-04 | 0 |  |  | With OTK as of 23rd march |  |  |  | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | iSupplier end to end integration flow | Not Applicable | 2026-03-04 | 2026-03-04 | 100% |  | TRUE | 1d | [5 empty] | 198 |  | 2026-03-04 | 2026-03-04 | 0 |  |  | With OTK as of 23rd march |  |  |  | Red
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | iSupplier TDD review | Not Applicable | 2026-03-05 | 2026-03-05 | 100% |  | TRUE | 1d | [5 empty] | 197 |  | 2026-03-05 | 2026-03-05 | 0 |  |  | with OTK as of 23rd march |  |  |  | Yellow
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Working integrations demo for iSupplier & Overall integration summary and next steps discussion | Not Applicable | 2026-03-05 | 2026-03-05 | 100% |  | TRUE | 1d | [5 empty] | 197 |  | 2026-03-05 | 2026-03-05 | 0 |  |  | TBD ,depends on 66,67,68 | Vinayaka Soratoor |  |  | Red
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Configuration Documentation Consolidation (offsite) | Completed | 2026-03-09 | 2026-03-20 | 100% |  |  | 10d | [5 empty] | 186 |  | 2026-02-27 | 2026-03-23 | 1d | [6 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | De-briefing session with internal Zycus Stakeholders | Completed | 2026-03-09 | 2026-03-09 | 100% |  |  | 1d | [5 empty] | 195 |  | 2026-03-09 | 2026-03-09 | 0 |  |  |  | Titan Core Project Team, Titan Project Manager, Zycus Project Manager, Zycus Project Team |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | S2C Configuration Documentation consolidation | Completed | 2026-03-18 | 2026-03-20 | 100% |  |  | 3d | [5 empty] | 186 |  | 2026-03-09 | 2026-03-13 | -5d | [6 empty] | Yellow
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Develop & Publish 1st draft of Implementation Approach Document (IAD) for iSupplier | Completed | 2026-03-18 | 2026-03-18 | 100% |  |  | 1d | [5 empty] | 188 | [7 empty] | shivani.mishra@zycus.com |  |  | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | iSupplier IAD Review and Sign off by Titan | Completed | 2026-03-19 | 2026-03-20 | 100% |  |  | 2d | [5 empty] | 186 | [7 empty] | courtney.re@Titan.com |  |  | Yellow
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Develop & Publish 1st draft of Implementation Approach Document (IAD) for iRequest | Completed | 2026-03-18 | 2026-03-18 | 100% |  |  | 1d | [5 empty] | 188 |  | 2026-03-09 | 2026-03-09 | -7d |  |  |  | Zycus Consultant |  |  | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | iRequest IAD Review and Sign off by Titan | Completed | 2026-03-19 | 2026-03-20 | 100% |  |  | 2d | [5 empty] | 186 |  | 2026-03-10 | 2026-03-11 | -7d |  |  |  | Titan Project Manager |  |  | Red
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Develop & Publish 1st draft of Implementation Approach Document (IAD) for iSource | Completed | 2026-03-18 | 2026-03-18 | 100% |  |  | 1d | [5 empty] | 188 |  | 2026-03-09 | 2026-03-09 | -7d |  |  |  | Zycus Consultant |  |  | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | iSource IAD Review and Sign off by Titan | Completed | 2026-03-19 | 2026-03-20 | 100% |  |  | 2d | [5 empty] | 186 |  | 2026-03-10 | 2026-03-12 | -6d |  |  |  | Titan Project Manager |  |  | Red
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Develop & Publish 1st draft of Implementation Approach Document (IAD) for iContract | Completed | 2026-03-18 | 2026-03-18 | 100% |  |  | 1d | [5 empty] | 188 |  | 2026-03-09 | 2026-03-09 | -7d |  |  |  | Zycus Consultant |  |  | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | iContract IAD Review and Sign off by Titan | Completed | 2026-03-19 | 2026-03-20 | 100% |  |  | 2d | [5 empty] | 186 |  | 2026-03-10 | 2026-03-13 | -5d |  |  |  | Titan Project Manager |  |  | Red
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Develop & Publish 1st draft of Implementation Approach Document (IAD) for iRisk | Completed | 2026-03-18 | 2026-03-18 | 100% |  |  | 1d | [5 empty] | 188 |  | 2026-03-09 | 2026-03-09 | -7d |  |  |  | Zycus Consultant |  |  | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | iRisk IAD Review and Sign off by Titan | Completed | 2026-03-19 | 2026-03-20 | 100% |  |  | 2d | [5 empty] | 186 |  | 2026-03-10 | 2026-03-13 | -5d |  |  |  | Titan Project Manager |  |  | Red
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Integration Configuration Documentation Consolidation | Completed | 2026-03-18 | 2026-03-20 | 100% |  |  | 3d | [5 empty] | 186 |  | 2026-03-05 | 2026-03-10 | -8d | [6 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Develop & Publish High Level Design Document TDD with Titan | Completed | 2026-03-18 | 2026-03-19 | 100% |  |  | 2d | [5 empty] | 187 |  | 2026-03-05 | 2026-03-10 | -7d |  |  |  | Zycus Integration Lead |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Titan to provide sign off on TDD indicating final requirements | Completed | 2026-03-20 | 2026-03-20 | 100% |  |  | 1d | [5 empty] | 186 |  | 2026-03-05 | 2026-03-05 | -11d |  |  |  | Titan Integration Team |  |  | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Functional Design Sign Off | Completed | 2026-03-20 | 2026-03-20 | 100% |  |  | 0 | [5 empty] | 187 | [10 empty] | Yellow
| #UNPARSEABLE | 1 | Aftab Hashambhai | 1 | Build |  | Red | Configuration and Build phase | In Progress | 2026-01-28 | 2026-05-19 | 98% |  |  | 80d | [5 empty] | 144 |  | 2026-03-05 | 2026-03-19 | -32d | [6 empty] | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Red | Functional Confuguration on Staging System/ Setup | In Progress | 2026-03-17 | 2026-04-20 | 93% |  |  | 25d | [5 empty] | 165 |  | 2026-03-05 | 2026-03-19 | -22d | [6 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Red | Update configurations based as per IAD (Solution Design) using agreed Commodity, Division Tree & Project Stages | In Progress | 2026-03-17 | 2026-04-20 | 93% |  |  | 25d | [5 empty] | 165 |  | 2026-03-11 | 2026-03-16 | -12d | [6 empty] | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | iRequest | Completed | 2026-03-23 | 2026-04-01 | 100% |  |  | 8d | [5 empty] | 178
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Request type and Request Definition configuration / updates | Completed | 2026-03-23 | 2026-03-23 | 100% |  |  | 1d | [5 empty] | 185 |  | 2026-03-11 | 2026-03-11 | -8d |  |  |  | sagar.chaurasiya@zycus.com |  |  | Green
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Review of configured Request forms and provide feedback | Completed | 2026-03-24 | 2026-03-24 | 100% |  |  | 1d | [5 empty] | 184 |  | 2026-03-11 | 2026-03-11 | -9d |  |  |  | sagar.chaurasiya@zycus.com |  |  | Green
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Zycus to update configurations of Request forms as per received feedback | Completed | 2026-03-25 | 2026-03-25 | 100% |  |  | 1d | [5 empty] | 183 |  | 2026-03-11 | 2026-03-11 | -10d |  |  |  | sagar.chaurasiya@zycus.com |  |  | Green
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Review of configured Request forms and provide confirmation | Completed | 2026-03-26 | 2026-03-26 | 100% |  |  | 1d | [5 empty] | 182 |  | 2026-03-11 | 2026-03-11 | -11d |  |  |  | courtney.re@Titan.com |  |  | Yellow
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | User Roles configuration | Completed | 2026-03-24 | 2026-03-24 | 100% |  |  | 1d | [5 empty] | 184 |  | 2026-03-11 | 2026-03-11 | -9d |  |  |  | sagar.chaurasiya@zycus.com |  |  | Green
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Approval workflow configuration | Completed | 2026-03-24 | 2026-03-24 | 100% |  |  | 1d | [5 empty] | 184 |  | 2026-03-11 | 2026-03-11 | -9d |  |  |  | sagar.chaurasiya@zycus.com |  |  | Green
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Review of User Roles and Approval Workflow and provide feedback | Completed | 2026-03-25 | 2026-03-25 | 100% |  |  | 1d | [5 empty] | 183 |  | 2026-03-11 | 2026-03-11 | -10d |  |  |  | courtney.re@Titan.com |  |  | Green
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Zycus to update configurations for user roles and approval workflow as per received feedback | Completed | 2026-03-26 | 2026-03-26 | 100% |  |  | 1d | [5 empty] | 182 |  | 2026-03-11 | 2026-03-11 | -11d |  |  |  | sagar.chaurasiya@zycus.com |  |  | Green
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Review of User Roles and Approval Workflow and provide confirmation | Completed | 2026-03-27 | 2026-03-27 | 100% |  |  | 1d | [5 empty] | 181 |  | 2026-03-11 | 2026-03-11 | -12d |  |  |  | courtney.re@Titan.com |  |  | Green
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Admin settings configuration | Completed | 2026-03-30 | 2026-03-31 | 100% |  |  | 2d | [5 empty] | 179 |  | 2026-03-13 | 2026-03-16 | -11d |  |  |  | Zycus Product Specialist |  |  | Green
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Readiness for Pre-UAT | Completed | 2026-04-01 | 2026-04-01 | 100% |  |  | 1d | [5 empty] | 178 | [7 empty] | abhilasha.s@zycus.com |  |  | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | iRisk Management | Completed | 2026-03-23 | 2026-04-03 | 100% |  |  | 10d | [5 empty] | 176 |  | 2026-03-09 | 2026-03-09 | -19d | [6 empty] | Yellow
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Conclude Functional Configuration | Completed | 2026-03-23 | 2026-03-23 | 100% |  |  | 1d | [5 empty] | 185 |  | 2026-03-09 | 2026-03-09 | -10d |  |  |  | sagar.chaurasiya@zycus.com |  |  | Yellow
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Configure KPI, Scorecards and Reports in iRisk pre PRODUCTION environment | Completed | 2026-03-23 | 2026-03-23 | 100% |  |  | 1d | [5 empty] | 185 |  | 2026-03-09 | 2026-03-09 | -10d |  |  |  | sagar.chaurasiya@zycus.com |  |  | Green
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Share Supplier Bulk upload template by Zycus | Completed | 2026-03-24 | 2026-03-24 | 100% |  |  | 1d | [5 empty] | 184 |  | 2026-03-09 | 2026-03-09 | -11d |  |  |  | sagar.chaurasiya@zycus.com |  |  | Green
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Run a mock event to verify the results | Completed | 2026-03-25 | 2026-03-25 | 100% |  |  | 1d | [5 empty] | 183 |  | 2026-03-09 | 2026-03-09 | -12d |  |  |  | sagar.chaurasiya@zycus.com |  |  | Red
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Configuration for SCAR & Development program on STAGING | Completed | 2026-03-25 | 2026-03-25 | 100% |  |  | 1d | [5 empty] | 183 |  | 2026-03-09 | 2026-03-09 | -12d |  |  |  | sagar.chaurasiya@zycus.com |  |  | Green
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Approval workflow configuration | Completed | 2026-03-26 | 2026-03-26 | 100% |  |  | 1d | [5 empty] | 182 |  | 2026-03-09 | 2026-03-09 | -13d |  |  |  | sagar.chaurasiya@zycus.com |  |  | Green
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Review cycles of entire iRisk process flow with the Titan | Completed | 2026-03-27 | 2026-03-27 | 100% |  |  | 1d | [5 empty] | 181 |  | 2026-03-09 | 2026-03-09 | -14d |  |  |  | sagar.chaurasiya@zycus.com |  |  | Red
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Titan to provide feedback | Completed | 2026-03-30 | 2026-03-30 | 100% |  |  | 1d | [5 empty] | 180 |  | 2026-03-09 | 2026-03-09 | -15d |  |  |  | sagar.chaurasiya@zycus.com |  |  | Red
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Zycus to incorporate the feedback | Completed | 2026-03-31 | 2026-03-31 | 100% |  |  | 1d | [5 empty] | 179 |  | 2026-03-09 | 2026-03-09 | -16d |  |  |  | sagar.chaurasiya@zycus.com |  |  | Red
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Titan to review and approve STAGING configuration | Completed | 2026-04-01 | 2026-04-01 | 100% |  |  | 1d | [5 empty] | 178 |  | 2026-03-09 | 2026-03-09 | -17d |  |  |  | courtney.re@Titan.com |  |  | Red
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Provide final list of users with specified roles | Completed | 2026-04-02 | 2026-04-02 | 100% |  |  | 1d | [5 empty] | 177 |  | 2026-03-09 | 2026-03-09 | -18d |  |  |  | Titan Core Project Team |  |  | Green
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Readiness for Pre-UAT | Completed | 2026-04-03 | 2026-04-03 | 100% |  |  | 1d | [5 empty] | 176 |  | 2026-03-09 | 2026-03-09 | -19d | [6 empty] | Red
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | iSource Management | Completed | 2026-03-23 | 2026-04-03 | 100% |  |  | 10d | [5 empty] | 176 |  | 2026-03-06 | 2026-03-06 | -20d | [6 empty] | Yellow
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | iSource: Conclude Functional Configuration | Completed | 2026-03-23 | 2026-03-23 | 100% |  |  | 1d | [5 empty] | 185 |  | 2026-03-06 | 2026-03-06 | -11d | [6 empty] | Green
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Functional Configuration on STAGING set Up | Completed | 2026-03-24 | 2026-03-24 | 100% |  |  | 1d | [5 empty] | 184 |  | 2026-03-06 | 2026-03-06 | -12d | [6 empty] | Green
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Configure Fields structures as per finalized UI template on STAGING environment | Completed | 2026-03-25 | 2026-03-25 | 100% |  |  | 1d | [5 empty] | 183 |  | 2026-03-06 | 2026-03-06 | -13d |  |  |  | Zycus Product Specialist |  |  | Green
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Workflow configuration on STAGING | Completed | 2026-03-26 | 2026-03-26 | 100% |  |  | 1d | [5 empty] | 182 |  | 2026-03-06 | 2026-03-06 | -14d |  |  |  | Zycus Product Specialist |  |  | Green
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Template Configuration on STAGING | Completed | 2026-03-27 | 2026-03-27 | 100% |  |  | 1d | [5 empty] | 181 |  | 2026-03-06 | 2026-03-06 | -15d |  |  |  | Zycus Product Specialist |  |  | Green
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Review cycles of entire Sourcing process flow with the Titan | Completed | 2026-03-30 | 2026-03-30 | 100% |  |  | 1d | [5 empty] | 180 |  | 2026-03-06 | 2026-03-06 | -16d |  |  |  | Zycus Product Specialist |  |  | Yellow
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Titan to provide feedback | Completed | 2026-03-31 | 2026-03-31 | 100% |  |  | 1d | [5 empty] | 179 |  | 2026-03-06 | 2026-03-06 | -17d |  |  |  | Zycus Product Specialist |  |  | Red
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Zycus to incorporate feedback | Completed | 2026-04-02 | 2026-04-03 | 100% |  |  | 2d | [5 empty] | 176 |  | 2026-03-06 | 2026-03-06 | -18d |  |  |  | Zycus Product Specialist |  |  | Red
| #UNPARSEABLE | 6 | Aftab Hashambhai | 6 |  |  | Green | Titan to review and approve STAGING configuration | Completed | 2026-04-02 | 2026-04-03 | 100% |  |  | 2d | [5 empty] | 176 |  | 2026-03-06 | 2026-03-06 | -20d |  |  |  | Titan Project Manager |  |  | Red
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | Provide final list of users with specified roles | Completed | 2026-04-02 | 2026-04-02 | 100% |  |  | 1d | [5 empty] | 177 |  | 2026-03-06 | 2026-03-06 | -19d |  |  |  | Titan Core Project Team |  |  | Green
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | Pre UAT preparedness | Completed | 2026-04-03 | 2026-04-03 | 100% |  |  | 1d | [5 empty] | 176 |  | 2026-03-06 | 2026-03-06 | -20d |  |  |  | Zycus Product Specialist |  |  | Yellow
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Contract Management with Integration and Merlin | Completed | 2026-03-23 | 2026-04-01 | 100% |  |  | 8d | [5 empty] | 178 |  | 2026-03-10 | 2026-03-10 | -16d | [6 empty] | Yellow
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Configure Fields structures as per finalized UI template on STAGING environment | Completed | 2026-03-23 | 2026-03-23 | 100% |  |  | 1d | [5 empty] | 185 |  | 2026-03-10 | 2026-03-10 | -9d |  |  |  | Zycus Product Specialist |  |  | Yellow
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Workflow configuration on STAGING | Completed | 2026-03-24 | 2026-03-24 | 100% |  |  | 1d | [5 empty] | 184 |  | 2026-03-10 | 2026-03-10 | -10d |  |  |  | Zycus Product Specialist |  |  | Yellow
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Template/Folder Configuration on STAGING | Completed | 2026-03-25 | 2026-03-25 | 100% |  |  | 1d | [5 empty] | 183 |  | 2026-03-10 | 2026-03-10 | -11d |  |  |  | Zycus Product Specialist |  |  | Yellow
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Provide access to required users on STAGING setup for Pre UAT | Completed | 2026-03-26 | 2026-03-26 | 100% |  |  | 1d | [5 empty] | 182 |  | 2026-03-10 | 2026-03-10 | -12d |  |  |  | Zycus Product Specialist |  |  | Yellow
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Review cycles of entire Contracting process flow with the Titan and Titan to provide feedback - if any | Completed | 2026-03-27 | 2026-03-27 | 100% |  |  | 1d | [5 empty] | 181 |  | 2026-03-10 | 2026-03-10 | -13d |  |  |  | Titan Project Team, Zycus Product Specialist |  |  | Yellow
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Zycus to incorporate feedback - as applicable | Completed | 2026-03-30 | 2026-03-30 | 100% |  |  | 1d | [5 empty] | 180 |  | 2026-03-10 | 2026-03-10 | -14d |  |  |  | Zycus Product Specialist |  |  | Yellow
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Titan to review updated configurations and approve STAGING configuration | Completed | 2026-03-31 | 2026-03-31 | 100% |  |  | 1d | [5 empty] | 179 |  | 2026-03-10 | 2026-03-10 | -15d |  |  |  | Zycus Product Specialist |  |  | Yellow
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  |  | Contract Management with Integration and Merlin | Completed |  |  | 100% | [19 empty] | Yellow
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Provide final list of users with specified roles | Completed | 2026-04-01 | 2026-04-01 | 100% |  |  | 1d | [5 empty] | 178 |  | 2026-03-10 | 2026-03-10 | -16d |  |  |  | Titan Core Project Team |  |  | Yellow
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Red | Supplier Information Management with Integration | In Progress | 2026-03-17 | 2026-04-20 | 82% |  |  | 25d | [5 empty] | 165 |  | 2026-03-05 | 2026-03-05 | -32d | [6 empty] | Yellow
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Common Master | Completed | 2026-03-19 | 2026-03-20 | 100% |  |  | 2d | [5 empty] | 186 | [10 empty] | Yellow
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Red | iSupplier Deployment | In Progress | 2026-03-17 | 2026-04-20 | 81% |  |  | 25d | [5 empty] | 165 |  | 2026-03-05 | 2026-03-05 | -32d | [6 empty] | Red
| #UNPARSEABLE | 6 | Aftab Hashambhai | 6 |  |  | Red | Repo Sample Supplier Upload on STAGING for iSource/iContract/iRisk | In Progress | 2026-03-17 | 2026-04-20 | 81% |  |  | 25d | [5 empty] | 165 |  | 2026-03-05 | 2026-03-05 | -32d | [6 empty] | Green
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | Titan to provide sample 100 suppliers for STAGING as per REPO bulk upload template (For iContract/iSource/iRisk) | Completed | 2026-03-17 | 2026-03-17 | 100% |  |  | 1d | [5 empty] | 189 |  | 2026-03-05 | 2026-03-05 | -8d |  |  |  | courtney.re@Titan.com |  |  | Green
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | Zycus to bulk upload sample supplier data on STAGING in Repo fields | Completed | 2026-03-18 | 2026-03-18 | 100% |  |  | 1d | [5 empty] | 188 |  | 2026-03-05 | 2026-03-05 | -9d |  |  |  | sagar.chaurasiya@zycus.com |  |  | Yellow
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Red | Design & Development on STAGING Set UP | In Progress | 2026-03-19 | 2026-04-20 | 79% |  |  | 23d | [5 empty] | 165 |  | 2026-03-05 | 2026-03-05 | -32d | [6 empty] | Yellow
| #UNPARSEABLE | 8 | Aftab Hashambhai | 8 |  |  | Green | Zycus to Configure UI based on the feedback on Metadata template | Completed | 2026-03-19 | 2026-03-19 | 100% |  |  | 1d | [5 empty] | 187 |  | 2026-03-05 | 2026-03-05 | -10d |  |  |  | sagar.chaurasiya@zycus.com |  |  | Green
| #UNPARSEABLE | 8 | Aftab Hashambhai | 8 |  |  | Green | Supplier workflow configuration for Create, Edit, Activate & Deactivate | Completed | 2026-03-20 | 2026-03-20 | 100% |  |  | 1d | [5 empty] | 186 | [7 empty] | sagar.chaurasiya@zycus.com |  |  | Green
| #UNPARSEABLE | 8 | Aftab Hashambhai | 8 |  |  | Green | iSupplier reference Master | Completed | 2026-03-19 | 2026-03-19 | 100% |  |  | 1d | [5 empty] | 187 | [7 empty] | sagar.chaurasiya@zycus.com |  |  | Green
| #UNPARSEABLE | 8 | Aftab Hashambhai | 8 |  |  | Green | facility System Setup | Completed | 2026-03-19 | 2026-03-19 | 100% |  |  | 1d | [5 empty] | 187 | [7 empty] | sagar.chaurasiya@zycus.com |  |  | Green
| #UNPARSEABLE | 8 | Aftab Hashambhai | 8 |  | TRUE | Red | Supplier Notification template | On Hold | 2026-03-26 | 2026-03-26 | 0% | TRUE |  | 1d | [5 empty] | 182 | [7 empty] | courtney.re@Titan.com |  |  | Red
| #UNPARSEABLE | 8 | Aftab Hashambhai | 8 |  |  | Red | OTK to share D&B creds | On Hold | 2026-03-19 | 2026-03-19 | 0% | TRUE |  | 1d | [5 empty] | 187 | [7 empty] | courtney.re@Titan.com |  |  | Red
| #UNPARSEABLE | 8 | Aftab Hashambhai | 8 |  |  | Red | Enable D & B App | On Hold | 2026-03-24 | 2026-03-24 | 0% | TRUE |  | 1d | [5 empty] | 184 | [7 empty] | sagar.chaurasiya@zycus.com |  |  | Yellow
| #UNPARSEABLE | 8 | Aftab Hashambhai | 8 |  |  | Green | OTK to share API details for ISN | Completed | 2026-03-19 | 2026-03-19 | 100% |  |  | 1d | [5 empty] | 187 | [7 empty] | courtney.re@Titan.com |  |  | Green
| #UNPARSEABLE | 8 | Aftab Hashambhai | 8 |  |  | Green | Zycus to Check ISN custom configuration/ App | Completed | 2026-03-27 | 2026-03-27 | 100% |  |  | 1d | [5 empty] | 181 | [10 empty] | Yellow
| #UNPARSEABLE | 8 | Aftab Hashambhai | 8 |  |  | Green | Setup ISN integration | Completed | 2026-04-20 | 2026-04-20 | 100% |  |  | 1d | [5 empty] | 165 | [10 empty] | Red
| #UNPARSEABLE | 8 | Aftab Hashambhai | 8 |  |  | Green | ISupplier Demo without ISN integration | Completed | 2026-03-27 | 2026-03-27 | 100% |  |  | 1d | [5 empty] | 181 | [10 empty] | Red
| #UNPARSEABLE | 8 | Aftab Hashambhai | 8 |  |  | Green | Feedback for iSupplier walkthrough | Completed | 2026-03-30 | 2026-03-30 | 100% |  |  | 1d | [5 empty] | 180 | [10 empty] | Red
| #UNPARSEABLE | 8 | Aftab Hashambhai | 8 |  |  | Green | iSupplier feedback inforporation & re-demo | Completed | 2026-04-02 | 2026-04-02 | 100% |  |  | 1d | [5 empty] | 177 | [10 empty] | Red
| #UNPARSEABLE | 8 | Aftab Hashambhai | 8 |  |  | Green | Pre UAT readiness | Completed | 2026-04-03 | 2026-04-03 | 100% |  |  | 1d | [5 empty] | 176 | [7 empty] | abhilasha.s@zycus.com |  |  | Red
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Single Sign On | Completed | 2026-01-28 | 2026-02-05 | 100% |  |  | 7d | [5 empty] | 217 |  | 2026-01-27 | 2026-02-27 | 16d | [6 empty] | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Availability of Technical Team from Titan | Completed | 2026-01-28 | 2026-01-30 | 100% |  |  | 3d | [5 empty] | 221 |  | 2026-01-27 | 2026-01-27 | 0 |  |  |  | Titan Project Manager |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Zycus to share Process flow of SSO integration | Completed | 2026-01-28 | 2026-01-28 | 100% |  |  | 1d | [5 empty] | 223 |  | 2026-01-28 | 2026-01-28 | 0 |  |  |  | Zycus SSO Team |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Exchange of configuration files | Completed | 2026-01-29 | 2026-01-29 | 100% |  |  | 1d | [5 empty] | 222 |  | 2026-01-29 | 2026-01-29 | 0 |  |  |  | Titan IT Team, Zycus SSO Team |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Exchange of certificates to be used | Completed | 2026-01-29 | 2026-01-29 | 100% |  |  | 1d | [5 empty] | 222 |  | 2026-01-29 | 2026-01-29 | 0 |  |  |  | Titan IT Team, Zycus SSO Team |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Approach to be used for Single Sign On [Claims/Email Address etc.] | Completed | 2026-01-30 | 2026-01-30 | 100% |  |  | 1d | [5 empty] | 221 |  | 2026-01-30 | 2026-01-30 | 0 |  |  |  | Titan IT Team, Zycus SSO Team |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Configuration and Review | Completed | 2026-02-02 | 2026-02-05 | 100% |  |  | 4d | [5 empty] | 217 |  | 2026-02-02 | 2026-02-05 | 0 | [6 empty] | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Registration of Service Provider URL for client | Completed | 2026-02-02 | 2026-02-02 | 100% |  |  | 1d | [5 empty] | 220 |  | 2026-02-02 | 2026-02-02 | 0 |  |  |  | Zycus SSO Team |  |  | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Registration TMS URL specific to client | Completed | 2026-02-02 | 2026-02-02 | 100% |  |  | 1d | [5 empty] | 220 |  | 2026-02-02 | 2026-02-02 | 0 |  |  |  | Zycus SSO Team |  |  | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Configuration of Web Server for service Provider application | Completed | 2026-02-03 | 2026-02-03 | 100% |  |  | 1d | [5 empty] | 219 |  | 2026-02-03 | 2026-02-03 | 0 |  |  |  | Zycus SSO Team |  |  | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Service Provider application deployment for client and sanity of the deployed setup | Completed | 2026-02-03 | 2026-02-03 | 100% |  |  | 1d | [5 empty] | 219 |  | 2026-02-03 | 2026-02-03 | 0 |  |  |  | Zycus SSO Team |  |  | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Configuration of Service Provider setup using below mentioned files | Completed | 2026-02-03 | 2026-02-03 | 100% |  |  | 1d | [5 empty] | 219 |  | 2026-02-03 | 2026-02-03 | 0 |  |  |  | Zycus SSO Team |  |  | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Issue Resolution, if any | Completed | 2026-02-04 | 2026-02-05 | 100% |  |  | 2d | [5 empty] | 217 |  | 2026-02-04 | 2026-02-05 | 0 |  |  |  | Zycus SSO Team |  |  | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Sign off of SSO on STAGING Environment | Completed | 2026-02-05 | 2026-02-05 | 100% |  |  | 1d | [5 empty] | 217 |  | 2026-02-05 | 2026-02-05 | 0 |  |  |  | Titan IT Team |  |  | Green
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Integration Build & SIT | Completed | 2026-03-23 | 2026-05-19 | 100% |  |  | 42d | [5 empty] | 144 | [10 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Systems Integration on STAGING Set UP | Completed | 2026-03-23 | 2026-04-14 | 100% |  |  | 17d | [5 empty] | 169 |  | 2026-02-24 | 2026-04-17 | 3d | [6 empty] | Yellow
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Integration set up, Development at Zycus | Completed | 2026-03-23 | 2026-03-30 | 100% |  |  | 6d | [5 empty] | 180 |  | 2026-03-06 | 2026-03-13 | -11d |  |  |  | Zycus Integration Team |  |  | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Integration set up, Development at Titan | Completed | 2026-03-23 | 2026-04-08 | 100% |  |  | 13d | [5 empty] | 173 |  | 2026-03-09 | 2026-03-27 | -8d |  |  |  | Titan Integration Team |  |  | Yellow
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Integration Unit Testing and Feedback Incorporation | Completed | 2026-04-09 | 2026-04-14 | 100% |  |  | 4d | [5 empty] | 169 |  | 2026-04-13 | 2026-04-16 | 2d |  |  |  | Titan Integration Team, Zycus Integration Team |  |  | Red
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Systems Integration Testing | Completed | 2026-04-15 | 2026-05-19 | 100% |  |  | 25d | [5 empty] | 144 |  | 2026-03-30 | 2026-04-17 | -11d | [6 empty] | Red
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | SIT on STAGING Set Up | Completed | 2026-04-15 | 2026-05-19 | 100% |  |  | 25d | [5 empty] | 144 |  | 2026-03-30 | 2026-04-17 | -11d |  |  |  | Titan Integration Team, Zycus Integration Specialist |  |  | Red
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Sign off on SIT | Completed | 2026-04-15 | 2026-05-19 | 100% |  |  | 25d | [5 empty] | 144 |  | 2026-03-30 | 2026-04-17 | -11d |  |  |  | Titan IT Project Manager |  |  | Red
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 | Pre UAT |  | Green | Pre UAT | Completed | 2026-04-02 | 2026-05-07 | 100% |  |  | 26d | [5 empty] | 152 |  | 2026-03-09 | 2026-04-17 | -14d | [6 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | iRequest -Prepare for UAT | Completed | 2026-04-02 | 2026-04-13 | 100% |  |  | 7.5d | [5 empty] | 170.5 |  | 2026-03-27 | 2026-04-17 | 4d | [6 empty] | Yellow
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Pre-UAT - Provide End to end walkthrough of configured iRequest to Titan | Completed | 2026-04-02 | 2026-04-02 | 100% |  |  | 1d | [5 empty] | 177 |  | 2026-03-27 | 2026-04-17 | 11d | [6 empty] | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Provide feedback - if any for iRequest configuration | Completed | 2026-04-03 | 2026-04-03 | 100% |  |  | 1d | [5 empty] | 176 |  | 2026-03-27 | 2026-04-17 | 10d | [6 empty] | Red
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Zycus to incorporate feedback - as applicable and share final version of Implementation Approach Document [IAD] | Completed | 2026-04-06 | 2026-04-06 | 100% |  |  | 1d | [5 empty] | 175 |  | 2026-03-27 | 2026-04-17 | 9d | [6 empty] | Red
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Sign off on Pre-UAT and final version of IAD | Completed | 2026-04-07 | 2026-04-07 | 100% |  |  | 1d | [5 empty] | 174 |  | 2026-03-27 | 2026-04-17 | 8d | [6 empty] | Red
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Logistics readiness if needed | Completed | 2026-04-07 | 2026-04-07 | 100% |  |  | 0 | [5 empty] | 175 |  | 2026-03-27 | 2026-04-17 | 8d | [6 empty] | Red
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Create users on STAGING set for UAT group | Completed | 2026-04-08 | 2026-04-08 | 100% |  |  | 1d | [5 empty] | 173 |  | 2026-03-27 | 2026-04-17 | 7d | [6 empty] | Red
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Quality Reviews | Completed | 2026-04-09 | 2026-04-09 | 100% |  |  | 0.5d | [5 empty] | 172.5 |  | 2026-03-27 | 2026-04-17 | 6.5d | [6 empty] | Red
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Schedule for quality check | Completed | 2026-04-09 | 2026-04-09 | 100% |  |  | 0.5d | [5 empty] | 172.5 |  | 2026-03-27 | 2026-04-17 | 6d | [6 empty] | Red
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Perform quality checks, PSRs as per quality checklist and submit to QC team | Completed | 2026-04-10 | 2026-04-10 | 100% |  |  | 0.5d | [5 empty] | 171.5 |  | 2026-03-27 | 2026-04-17 | 5.5d | [6 empty] | Red
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Quality Check by Zycus QC team | Completed | 2026-04-10 | 2026-04-10 | 100% |  |  | 0.5d | [5 empty] | 171.5 |  | 2026-03-27 | 2026-04-17 | 5d | [6 empty] | Red
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Release of iRequest STAGING to Titan key users (UAT Release) | Completed | 2026-04-13 | 2026-04-13 | 100% |  |  | 0.5d | [5 empty] | 170.5 |  | 2026-03-27 | 2026-04-17 | 4.5d | [6 empty] | Red
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Create users and assign roles on STAGING set for UAT group | Completed | 2026-04-13 | 2026-04-13 | 100% |  |  | 0.5d | [5 empty] | 170.5 |  | 2026-03-27 | 2026-04-17 | 4d | [6 empty] | Red
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | iRisk -Prepare for UAT | Completed | 2026-04-06 | 2026-04-09 | 100% |  |  | 4d | [5 empty] | 172 |  | 2026-03-10 | 2026-03-10 | -22d |  |  |  | Zycus Product Specialist |  |  | Yellow
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Pre-UAT | Completed | 2026-04-06 | 2026-04-09 | 100% |  |  | 4d | [5 empty] | 172 |  | 2026-03-10 | 2026-03-10 | -22d | [6 empty] | Yellow
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Pre-UAT - Provide End to end walkthrough of configured iRisk to Titan | Completed | 2026-04-06 | 2026-04-06 | 100% |  |  | 1d | [5 empty] | 175 |  | 2026-03-10 | 2026-03-10 | -19d |  |  |  | Titan Core Project Team, Zycus Consultant, Zycus Product Specialist |  |  | Green
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Provide feedback - if any for iRisk configuration | Completed | 2026-04-07 | 2026-04-07 | 100% |  |  | 1d | [5 empty] | 174 |  | 2026-03-10 | 2026-03-10 | -20d |  |  |  | Titan Project Team |  |  | Red
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Zycus to incorporate feedback - as applicable and share final version of Implementation Approach Document [IAD] | Completed | 2026-04-08 | 2026-04-08 | 100% |  |  | 1d | [5 empty] | 173 |  | 2026-03-10 | 2026-03-10 | -21d |  |  |  | Zycus Project Team |  |  | Red
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Sign off on Pre-UAT and final version of IAD | Completed | 2026-04-09 | 2026-04-09 | 100% |  |  | 1d | [5 empty] | 172 |  | 2026-03-10 | 2026-03-10 | -22d |  |  |  | Titan Project Manager |  |  | Red
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | iSource- Prepare for UAT | Completed | 2026-04-06 | 2026-04-09 | 100% |  |  | 4d | [5 empty] | 172 |  | 2026-03-09 | 2026-03-11 | -21d | [6 empty] | Yellow
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Pre-UAT - Provide End to end walkthrough of configured iSource to Titan | Completed | 2026-04-06 | 2026-04-06 | 100% |  |  | 1d | [5 empty] | 175 |  | 2026-03-09 | 2026-03-09 | -20d |  |  |  | Zycus Consultant, Zycus Product Specialist |  |  | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Provide feedback - if any for iSource configuration | Completed | 2026-04-07 | 2026-04-07 | 100% |  |  | 1d | [5 empty] | 174 |  | 2026-03-09 | 2026-03-09 | -21d |  |  |  | Titan Project Team |  |  | Red
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Incorporate issue resolution if any and share final version of IAD | Completed | 2026-04-08 | 2026-04-08 | 100% |  |  | 1d | [5 empty] | 173 |  | 2026-03-10 | 2026-03-10 | -21d |  |  |  | Zycus Project Team |  |  | Red
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Sign off on Pre-UAT and final version of IAD | Completed | 2026-04-09 | 2026-04-09 | 100% |  |  | 1d | [5 empty] | 172 |  | 2026-03-11 | 2026-03-11 | -21d |  |  |  | Titan Project Manager |  |  | Red
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Pre UAT iContract | Completed | 2026-04-02 | 2026-04-07 | 100% |  |  | 4d | [5 empty] | 174 |  | 2026-03-11 | 2026-04-17 | 8d |  |  |  | Zycus Product Specialist |  |  | Red
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Pre-UAT - Provide End to end walkthrough of configured iContract to Titan | Completed | 2026-04-02 | 2026-04-02 | 100% |  |  | 1d | [5 empty] | 177 |  | 2026-03-11 | 2026-03-11 | -16d |  |  |  | Titan Core Project Team, Zycus Consultant, Zycus Product Specialist |  |  | Red
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Provide feedback - if any for iContract configuration | Completed | 2026-04-03 | 2026-04-03 | 100% |  |  | 1d | [5 empty] | 176 |  | 2026-03-11 | 2026-03-11 | -17d |  |  |  | Titan Project Team |  |  | Red
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Zycus to incorporate feedback - as applicable and share final version of Implementation Approach Document [IAD] | Completed | 2026-04-06 | 2026-04-06 | 100% |  |  | 1d | [5 empty] | 175 |  | 2026-03-11 | 2026-03-11 | -18d |  |  |  | Zycus Consultant, Zycus Product Specialist |  |  | Red
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Sign off on Pre-UAT and final version of IAD sign off | Completed | 2026-04-07 | 2026-04-07 | 100% |  |  | 1d | [5 empty] | 174 |  | 2026-03-11 | 2026-04-17 | 8d |  |  |  | Titan Project Manager |  |  | Red
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  | TRUE | Green | iSupplier Pre UAT | Completed | 2026-04-06 | 2026-05-07 | 100% |  |  | 24d | [5 empty] | 152 | [10 empty] | Yellow
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Pre-UAT - Provide End to end walkthrough of configured iSupplier- Functional flow only | Completed | 2026-04-06 | 2026-04-07 | 100% |  |  | 2d | [5 empty] | 174 | [10 empty] | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | End to End flow for iSupplier with Integration | Completed | 2026-05-05 | 2026-05-06 | 100% |  |  | 2d | [5 empty] | 153 | [10 empty] | Red
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Provide feedback - if any for iSupplier configuration | Completed | 2026-04-08 | 2026-04-08 | 100% |  |  | 1d | [5 empty] | 173 | [10 empty] | Yellow
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Zycus to incorporate feedback - as applicable and share final version of Implementation Approach Document [IAD] | Completed | 2026-04-09 | 2026-04-09 | 100% |  |  | 1d | [5 empty] | 172 | [10 empty] | Yellow
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Sign off on Pre-UAT and final version of IAD | Completed | 2026-05-07 | 2026-05-07 | 100% |  |  | 1d | [5 empty] | 152 | [10 empty] | Yellow
| #UNPARSEABLE | 1 | Aftab Hashambhai | 1 | UAT |  | Green | UAT | Completed | 2026-05-04 | 2026-05-28 | 100% |  |  | 19d | [5 empty] | 137 |  | 2026-04-27 | 2026-05-08 | -10d | [6 empty] | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | UAT-iSource | Completed | 2026-05-04 | 2026-05-12 | 100% |  |  | 7d | [5 empty] | 149 |  | 2026-04-27 | 2026-05-08 | -2d | [6 empty] | Red
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | UAT of iSource on STAGING environment | Completed | 2026-05-04 | 2026-05-05 | 100% |  |  | 2d | [5 empty] | 154 |  | 2026-04-27 | 2026-05-08 | 3d |  |  |  | Titan Core Project Team, Zycus Consultant, Zycus Product Specialist |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Defect Analysis & UAT Feedback incorporation and share Test Closure Memo | Completed | 2026-05-05 | 2026-05-08 | 100% |  |  | 4d | [5 empty] | 151 |  | 2026-04-27 | 2026-05-08 | 0 |  |  |  | Zycus Project Team |  |  | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Titan to provide sign off on Test Closure Memo | Completed | 2026-05-11 | 2026-05-12 | 100% |  |  | 2d | [5 empty] | 149 |  | 2026-04-27 | 2026-05-08 | -2d |  |  |  | Titan Core Project Team, Titan Project Manager |  |  | Green
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | UAT- iRequest | Completed | 2026-05-04 | 2026-05-12 | 100% |  |  | 7d | [5 empty] | 149 |  | 2026-04-27 | 2026-05-08 | -2d | [6 empty] | Red
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | UAT of iRequest on STAGING environment | Completed | 2026-05-04 | 2026-05-05 | 100% |  |  | 2d | [5 empty] | 154 |  | 2026-04-27 | 2026-05-08 | 3d | [6 empty] | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Defect Analysis & UAT Feedback incorporation and share Test Closure Memo | Completed | 2026-05-05 | 2026-05-08 | 100% |  |  | 4d | [5 empty] | 151 |  | 2026-04-27 | 2026-05-08 | 0 | [6 empty] | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Titan to provide sign off on Test Closure Memo | Completed | 2026-05-11 | 2026-05-12 | 100% |  |  | 2d | [5 empty] | 149 |  | 2026-04-27 | 2026-05-08 | -2d | [6 empty] | Green
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | UAT -iContract | Completed | 2026-05-06 | 2026-05-14 | 100% |  |  | 7d | [5 empty] | 147 | [10 empty] | Red
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | UAT of iContract on STAGING environment | Completed | 2026-05-06 | 2026-05-07 | 100% |  |  | 2d | [5 empty] | 152 | [10 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Defect Analysis & UAT Feedback incorporation and share Test Closure Memo | Completed | 2026-05-07 | 2026-05-12 | 100% |  |  | 4d | [5 empty] | 149 | [10 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Titan to provide sign off on Test Closure Memo | Completed | 2026-05-13 | 2026-05-14 | 100% |  |  | 2d | [5 empty] | 147 | [10 empty] | Red
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | UAT -iRisk | Completed | 2026-05-06 | 2026-05-14 | 100% |  |  | 7d | [5 empty] | 147 |  | 2026-04-27 | 2026-05-08 | -4d | [6 empty] | Red
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | UAT of iRisk on STAGING environment | Completed | 2026-05-06 | 2026-05-07 | 100% |  |  | 2d | [5 empty] | 152 |  | 2026-04-27 | 2026-05-08 | 1d | [6 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Defect Analysis & UAT Feedback incorporation and share Test Closure Memo | Completed | 2026-05-07 | 2026-05-12 | 100% |  |  | 4d | [5 empty] | 147 |  | 2026-04-27 | 2026-05-08 | -2d | [6 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Titan to provide sign off on Test Closure Memo | Completed | 2026-05-13 | 2026-05-14 | 100% |  |  | 2d | 226 |  |  |  |  | 147 |  | 2026-04-27 | 2026-05-08 | -4d | [6 empty] | Red
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | UAT -iSupplier | Completed | 2026-05-11 | 2026-05-28 | 100% |  |  | 14d | [5 empty] | 137 |  | 2026-04-27 | 2026-05-08 | -10d | [6 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | UAT of iSupplier on STAGING environment | Completed | 2026-05-11 | 2026-05-18 | 100% |  |  | 6d | [5 empty] | 137 |  | 2026-04-27 | 2026-05-08 | -6d | [6 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Defect Analysis & UAT Feedback incorporation and share Test Closure Memo | Completed | 2026-05-19 | 2026-05-28 | 100% |  |  | 8d | 229 |  |  |  |  | 137 |  | 2026-04-27 | 2026-05-08 | -8d | [6 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Titan to provide sign off on Test Closure Memo | Completed | 2026-05-21 | 2026-05-22 | 100% |  |  | 2d | [5 empty] | 141 |  | 2026-04-27 | 2026-05-08 | -10d | [6 empty] | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | UAT Sign Off | Completed | 2026-05-22 | 2026-05-22 | 100% |  |  | 0 | [5 empty] | 142 | [10 empty] | Yellow
| #UNPARSEABLE | 1 | Aftab Hashambhai | 1 | TTT |  | Green | Train The Trainer | Completed | 2026-05-14 | 2026-06-19 | 100% |  |  | 27d | [5 empty] | 121 |  | 2026-05-11 | 2026-05-22 | -16d | [6 empty] | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Training Preparation | Completed | 2026-05-14 | 2026-05-27 | 100% |  |  | 10d | [5 empty] | 138 |  | 2026-05-11 | 2026-05-14 | -9d | [6 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Training Approach and Schedule finalization | Completed | 2026-05-14 | 2026-05-15 | 100% |  |  | 2d | [5 empty] | 146 |  | 2026-05-11 | 2026-05-12 | -10d |  |  |  | Titan Project Manager, Zycus Project Manager, Zycus University |  |  | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Training Agenda Finalization | Completed | 2026-05-15 | 2026-05-15 | 100% |  |  | 1d | [5 empty] | 146 |  | 2026-05-11 | 2026-05-12 | -11d |  |  |  | Titan Project Manager, Zycus University |  |  | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Logistics arrangement for Training | Not Applicable | 2026-05-27 | 2026-05-27 | 100% |  | TRUE | 1d | [5 empty] | 138 |  | 2026-05-13 | 2026-05-14 | -9d |  |  |  | Zycus Project Manager |  |  | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Train The Trainer Sessions | Completed | 2026-05-19 | 2026-06-05 | 100% |  |  | 14d | [5 empty] | 131 | [10 empty] | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | End User trainings | Completed | 2026-06-15 | 2026-06-19 | 100% |  |  | 5d | [5 empty] | 121 | [10 empty] | Yellow
| #UNPARSEABLE | 1 | Aftab Hashambhai | 1 | Migration |  | Red | Production & Cutover | In Progress | 2026-05-04 | 2026-06-12 | 97% |  |  | 30d | [5 empty] | 126 |  | 2026-02-06 | 2026-07-02 | 15d | [6 empty] | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Production System Standard Setup | Completed | 2026-05-04 | 2026-05-06 | 100% |  |  | 3d | [5 empty] | 131 |  | 2026-05-11 | 2026-05-22 | 12d | [6 empty] | Red
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | SSO and Integration Setup | Completed | 2026-05-07 | 2026-06-05 | 100% |  |  | 22d | 241 |  |  |  |  | 131 |  | 2026-05-11 | 2026-05-22 | -2d | [6 empty] | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | User list to be provide with access mapping by customer | Completed | 2026-05-07 | 2026-05-07 | 100% |  |  | 1d | 241 |  |  |  |  | 152
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Red | Supplier data to be provided by Customer | In Progress | 2026-05-04 | 2026-06-05 | 80% |  |  | 25d |  |  | sagar.chaurasiya@zycus.com |  |  | 131
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | iContract Legacy data to be provided by customer | Not Applicable | 2026-05-18 | 2026-06-05 | 100% |  | TRUE | 15d | [5 empty] | 131
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | User Setup | Completed | 2026-05-08 | 2026-06-05 | 100% |  |  | 21d |  |  | sagar.chaurasiya@zycus.com |  |  | 131 |  | 2026-05-11 | 2026-05-22 | 13d | [6 empty] | Red
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | User Upload | Completed | 2026-05-12 | 2026-06-05 | 100% |  |  | 19d |  |  | sagar.chaurasiya@zycus.com |  |  | 131 | [10 empty] | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | iRequest | Completed | 2026-05-18 | 2026-06-05 | 100% |  |  | 15d | [5 empty] | 131 | [10 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Production Deployment & Readiness-Migrate Solution from Staging to Prodcution | Completed | 2026-05-18 | 2026-06-05 | 100% |  |  | 15d |  |  | sagar.chaurasiya@zycus.com |  |  | 131 | [10 empty] | Red
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | iSource | Completed | 2026-05-18 | 2026-06-05 | 100% |  |  | 15d | [5 empty] | 131 | [10 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Production Deployment & Readiness-Migrate Solution from Staging to Prodcution | Completed | 2026-05-18 | 2026-06-05 | 100% |  |  | 15d | [5 empty] | 131 |  | 2026-05-11 | 2026-05-22 | 6d | [6 empty] | Red
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | iContract | Completed | 2026-05-18 | 2026-06-05 | 100% |  |  | 15d | [5 empty] | 131 | [10 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Production Deployment & Readiness-Migrate Solution from Staging to Prodcution | Completed | 2026-05-18 | 2026-06-05 | 100% |  |  | 15d | [5 empty] | 131 | [10 empty] | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | iRisk | Completed | 2026-05-18 | 2026-06-05 | 100% |  |  | 15d | [5 empty] | 131 | [10 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Production Deployment & Readiness-Migrate Solution from Staging to Prodcution | Completed | 2026-05-18 | 2026-06-05 | 100% |  |  | 15d | [5 empty] | 131 | [10 empty] | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | iSupplier | Completed | 2026-05-18 | 2026-06-05 | 100% |  |  | 15d | [5 empty] | 131 | [10 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Production Deployment & Readiness-Migrate Solution from Staging to Prodcution | Completed | 2026-05-18 | 2026-06-05 | 100% |  |  | 15d | [5 empty] | 131 | [10 empty] | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Data Load-Historical and bulk upload - iSupplier | Completed | 2026-06-08 | 2026-06-09 | 100% |  |  | 2d | [5 empty] | 129 | [10 empty] | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Red | Data Load-Historical and bulk upload - iContract | In Progress | 2026-06-08 | 2026-06-09 | 90% |  |  | 2d | [5 empty] | 129 |  | 2026-05-11 | 2026-05-22 | -12d | [6 empty] | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Integration Setup from OTK side | Completed | 2026-05-25 | 2026-06-09 | 100% |  |  | 12d | [5 empty] | 129 | [10 empty] | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Sanity Check of Production system | Completed | 2026-06-09 | 2026-06-11 | 100% |  |  | 3d | [5 empty] | 127 | [10 empty] | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Go/No-go Check Point ( Meeting with Titan) | Completed | 2026-06-12 | 2026-06-12 | 100% |  |  | 1d | [5 empty] | 126 |  | 2026-05-28 | 2026-05-28 | -7d |  |  |  | Titan Core Project Team, Titan Project Manager, Zycus Project Manager |  |  | Yellow
| #UNPARSEABLE | 1 | Aftab Hashambhai | 1 | Go Live |  | Green | Go-Live & Support intro | Completed | 2026-06-16 | 2026-06-16 | 100% |  |  | 1d | [5 empty] | 122 |  | 2026-05-29 | 2026-05-29 | -8d | [6 empty] | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Go live | Completed | 2026-06-16 | 2026-06-16 | 100% |  |  | 1d | [5 empty] | 104 |  | 2026-05-29 | 2026-05-29 | -8d | [6 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Release iRequest to all users | Completed | 2026-06-16 | 2026-06-16 | 100% |  |  | 1d | [5 empty] | 124 |  | 2026-05-29 | 2026-05-29 | -8d | [6 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Release iContract to all users (Soft Launch or Full Launch based on Titan decision) Go-live Sign-off | Completed | 2026-06-16 | 2026-06-16 | 100% |  |  | 1d | [5 empty] | 124 |  | 2026-05-29 | 2026-05-29 | -8d | [6 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Release iRisk to all users (Pilot Launch or Full Launch based on Titan decision) | Completed | 2026-06-16 | 2026-06-16 | 100% |  |  | 1d | [5 empty] | 124 |  | 2026-05-29 | 2026-05-29 | -8d | [6 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Release iSupplier to all users (Pilot Launch or Full Launch based on Titan decision) Go-live Sign-off | Completed | 2026-06-16 | 2026-06-16 | 100% |  |  | 1d | [5 empty] | 124 |  | 2026-05-29 | 2026-05-29 | -8d | [6 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Release iSource to all users (Pilot Launch or Full Launch based on Titan decision) Go-live Sign-off | Completed | 2026-06-16 | 2026-06-16 | 100% |  |  | 1d | [5 empty] | 124 |  | 2026-05-29 | 2026-05-29 | -8d |  |  |  | Zycus Product Specialist |  |  | Yellow
| #UNPARSEABLE | 1 | Aftab Hashambhai | 1 | Hypercare |  | Red | Hyper Care(Measure and Adoption) Solution | In Progress | 2026-06-17 | 2026-07-14 | 6% |  |  | 20d | [5 empty] | 104 |  | 2026-05-29 | 2026-05-29 | -30d | [6 empty] | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Red | Onboard and Introduce TAM team to Customer | In Progress | 2026-06-18 | 2026-06-18 | 90% |  |  | 1d | 263FS +1d |  | Aftab Hashambhai |  |  | 121 |  | 2026-05-29 | 2026-05-29 | -10d | [6 empty] | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Red | Walkthrough of post hypercare support process by TAM team | In Progress | 2026-06-19 | 2026-06-19 | 50% |  |  | 1d | 271 |  | Aftab Hashambhai |  |  | 121 |  | 2026-05-29 | 2026-05-29 | -11d | [6 empty] | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Red | Hypercare Support | Not Started | 2026-06-17 | 2026-07-14 |  |  |  | 20d | 264 |  |  |  |  | 104 | [10 empty] | Yellow
| #UNPARSEABLE | 0 | Aftab Hashambhai | 0 |  |  | Red | Phase 2 - P2P | In Progress | 2026-04-22 | 2026-12-07 | 21% |  |  | 164d | [5 empty] | 0 |  | 2026-04-15 | 2026-08-10 | -81d | [6 empty] | Yellow
| #UNPARSEABLE | 1 | Aftab Hashambhai | 1 |  |  | Green | Project Initiation & Data Gathering | Completed | 2026-04-22 | 2026-06-02 | 100% |  |  | 30d | [5 empty] | 134 |  | 2026-04-15 | 2026-04-30 | -15d | [6 empty] | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Zycus BootCamp | Completed | 2026-04-22 | 2026-04-23 | 100% |  |  | 2d | [5 empty] | 162 | [10 empty] | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | eProc | Completed | 2026-04-22 | 2026-04-22 | 100% |  |  | 1d | [5 empty] | 163 | [10 empty] | Green
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | eInvoice | Completed | 2026-04-23 | 2026-04-23 | 100% |  |  | 1d | [5 empty] | 162 | [10 empty] | Green
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Logistics Activities | Completed | 2026-05-18 | 2026-06-02 | 100% |  |  | 12d | [5 empty] | 134 |  | 2026-04-15 | 2026-04-20 | -9d | [6 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Discuss & Finalize Logistics activity dates - as required | Completed | 2026-05-18 | 2026-05-22 | 100% |  |  | 5d | [5 empty] | 141 |  | 2026-04-15 | 2026-04-15 | -8d |  |  |  | Titan Core Project Team, Titan Project Manager, Zycus Project Manager |  |  | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Share Logistics Plan - if any with Titan | Completed | 2026-05-25 | 2026-05-29 | 100% |  |  | 5d | [5 empty] | 136 |  | 2026-04-16 | 2026-04-16 | -9d |  |  |  | Titan Core Project Team, Titan Project Manager, Zycus Project Manager |  |  | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Review & Approve Logistics Plan | Completed | 2026-06-01 | 2026-06-01 | 100% |  |  | 1d | [5 empty] | 135 |  | 2026-04-17 | 2026-04-17 | -9d |  |  |  | Titan Project Manager |  |  | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Arrange Logistics required for workshop | Completed | 2026-06-02 | 2026-06-02 | 100% |  |  | 1d | [5 empty] | 134 |  | 2026-04-20 | 2026-04-20 | -9d |  |  |  | Zycus Project Manager, Zycus Project Team |  |  | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Data Gathering & STAGING Set Up | Completed | 2026-04-28 | 2026-05-22 | 100% |  |  | 19d | [5 empty] | 141 |  | 2026-04-15 | 2026-04-30 | -15d | [6 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Discussion on Pre-Requisites as per agenda shared | Completed | 2026-04-28 | 2026-05-22 | 100% |  |  | 19d | [5 empty] | 141 |  | 2026-04-15 | 2026-04-30 | -15d | [6 empty] | Yellow
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Sessions as per Pre-Requisite agenda | Completed | 2026-04-28 | 2026-04-30 | 100% |  |  | 3d | [5 empty] | 157 |  | 2026-04-15 | 2026-04-28 | -2d |  |  |  | Titan Core Project Team, Zycus Project Team |  |  | Green
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Pre workshop discussion for Integration | Completed | 2026-05-18 | 2026-05-22 | 100% |  |  | 5d | [5 empty] | 141 |  | 2026-04-29 | 2026-04-30 | -11d | [6 empty] | Yellow
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Titan As-Is Discussion | Completed | 2026-05-11 | 2026-05-14 | 100% |  |  | 4d | [5 empty] | 147 | [10 empty] | Yellow
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Data gathering | Completed | 2026-05-01 | 2026-05-22 | 100% |  |  | 16d | [5 empty] | 141 | [10 empty] | Yellow
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  | TRUE | Green | Share Pre-Requisite documents and information as per the templates shared by Zycus with Samples | Completed | 2026-05-01 | 2026-05-22 | 100% |  |  | 16d | [5 empty] | 141 |  | 2026-04-15 | 2026-04-16 | -25d |  |  |  | Titan Core Project Team, Titan Project Manager |  |  | Yellow
| #UNPARSEABLE | 1 | Aftab Hashambhai | 1 |  |  | Red | Configuration Documentation workshop | In Progress | 2026-06-22 | 2026-07-13 | 25% |  |  | 16d | [5 empty] | 105 |  | 2026-04-21 | 2026-05-26 | -43d | [6 empty] | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  | TRUE | Green | P2P, iSupplier Configuration Documentation Workshop | Completed | 2026-06-22 | 2026-06-26 | 100% |  |  | 5d | [5 empty] | 88 |  | 2026-04-21 | 2026-05-04 | -22d |  |  |  | Titan Core Project Team, Titan Project Manager, Zycus Merlin Product Team, Zycus Project Manager, Zycus Project Team |  |  | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Red | Master data to be provided by OTK team | Not Started | 2026-06-26 | 2026-07-02 |  |  |  | 5d |  |  |  |  | High | 88
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Red | Workflow details & CULT table details to be provided by OTK | Not Started | 2026-06-26 | 2026-07-10 |  |  |  | 11d | [5 empty] | 106
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Develop & Publish 1st draft of Implementation Approach Document (IAD) for eProc-eInvoice | Not Started | 2026-07-07 | 2026-07-09 | 0% |  |  | 3d | 292, 293FS +2d |  |  |  |  | 88 |  | 2026-05-12 | 2026-05-12 | -24d |  |  |  | Zycus Consultant |  |  | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | eProc-eInvoice IAD Review and Sign off by Titan | Not Started | 2026-07-10 | 2026-07-13 | 0% |  |  | 2d | 295 |  |  |  |  | 88 |  | 2026-05-13 | 2026-05-13 | -25d |  |  |  | Titan Project Manager |  |  | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Yellow | P2P Integration Design | In Progress | 2026-06-29 | 2026-07-10 | 39% |  |  | 10d | [5 empty] | 106 | [10 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Red | eInvoice outbound | In Progress | 2026-06-29 | 2026-06-29 | 90% |  |  | 1d | [5 empty] | 115 |  | 2026-05-12 | 2026-05-19 | -22d | [6 empty] | Yellow
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Red | eInvoice integration use cases discussion-Invoice,creditmemo,payment,apportionment | In Progress | 2026-06-29 | 2026-06-29 | 90% |  |  | 1d | [5 empty] | 115 |  | 2026-05-12 | 2026-05-13 | -22d | [6 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Red | eProc Direct & Indirect | In Progress | 2026-06-30 | 2026-07-01 | 90% |  |  | 2d | [5 empty] | 113 |  | 2026-05-12 | 2026-05-18 | -30d | [6 empty] | Yellow
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Red | eProc integration use cases discussion-create,edit,cancel,close | In Progress | 2026-06-30 | 2026-07-01 | 90% |  |  | 2d | [5 empty] | 113 |  | 2026-05-12 | 2026-05-12 | -30d | [6 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Master data inbound | Not Started | 2026-07-07 | 2026-07-08 | 0% |  |  | 2d | [5 empty] | 108 |  | 2026-05-12 | 2026-05-13 | -44d | [6 empty] | Yellow
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Master data discussion overall and connectivity-2 master data-Increase the days based on master data count including DDT/DMT | Not Started | 2026-07-07 | 2026-07-08 | 0% |  |  | 2d | [5 empty] | 89 |  | 2026-05-12 | 2026-05-12 | -42d | [6 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Review and feedback incorporation | Not Started | 2026-07-09 | 2026-07-09 | 0% |  |  | 1d | 303 |  |  |  |  | 89 | [7 empty] | Titan Integration Team, Titan Project Manager, Zycus Consultant, Zycus Integration Specialist |  |  | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Sign off on LLD | Not Started | 2026-07-10 | 2026-07-10 | 0% |  |  | 1d | 304 |  |  |  |  | 89 | [7 empty] | Titan Project Manager |  |  | Yellow
| #UNPARSEABLE | 1 | Aftab Hashambhai | 1 |  |  | Green | Configuration and Build phase | Not Started | 2026-07-13 | 2026-09-03 |  |  |  | 39d | [5 empty] | 67
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | eInvoice Config, Pre-UAT, Integration Design & Development and SIT | Not Started | 2026-07-13 | 2026-09-03 |  |  |  | 39d | [5 empty] | 67
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Functional Configuration Finalization on STAGING set Up | Not Started | 2026-07-14 | 2026-08-07 |  |  |  | 19d | [5 empty] | 86
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | User Roles configuration | Not Started | 2026-07-14 | 2026-07-15 |  |  |  | 2d | 296 |  |  |  |  | 88
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Admin settings configuration | Not Started | 2026-07-16 | 2026-07-17 |  |  |  | 2d | 309 |  |  |  |  | 88
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Configure Workflow | Not Started | 2026-07-20 | 2026-07-24 |  |  |  | 5d | 310 |  |  |  |  | 88
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Readiness for Pre-UAT | Not Started | 2026-07-27 | 2026-07-28 |  |  |  | 2d | 311 |  |  |  |  | 88
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Pre-UAT on STAGING | Not Started | 2026-07-27 | 2026-08-07 |  |  |  | 10d | [5 empty] | 86
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Pre-UAT - Provide End to end walkthrough of configured eProc to the Customer | Not Started | 2026-07-29 | 2026-07-31 |  |  |  | 3d | 312 |  |  |  |  | 88
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Pre-UAT for eInvoice | Not Started | 2026-08-03 | 2026-08-05 |  |  |  | 3d | 314 |  |  |  |  | 88
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Provide feedback - if any for eProc configuration | Not Started | 2026-07-27 | 2026-07-30 |  |  |  | 4d | [5 empty] | 55
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Zycus to incorporate feedback - as applicable and share final version of Implementation Approach Document [IAD] | Not Started | 2026-07-31 | 2026-08-06 |  |  |  | 5d | 316 |  |  |  |  | 55
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Sign off on Pre-UAT and final version of IAD | Not Started | 2026-08-07 | 2026-08-07 |  |  |  | 1d | 317 |  |  |  |  | 55
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | eInvoice : Conclude Functional Configuration | Not Started | 2026-08-10 | 2026-08-10 |  |  |  | 1d | 318 |  |  |  |  | 55
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | eInvoice Integration | Not Started | 2026-07-13 | 2026-09-03 |  |  |  | 39d | [5 empty] | 67
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Integration Design | Not Started | 2026-07-13 | 2026-07-21 |  |  |  | 7d | [5 empty] | 99
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Mapping activity for Integration | Not Started | 2026-07-13 | 2026-07-14 |  |  |  | 2d | 305 |  |  |  |  | 99
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Share TDD for interface | Not Started | 2026-07-15 | 2026-07-15 |  |  |  | 1d | 322 |  |  |  |  | 99
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Review of TDD and share feedback with Zycus | Not Started | 2026-07-16 | 2026-07-17 |  |  |  | 2d | 323 |  |  |  |  | 99
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Sign off on TDD | Not Started | 2026-07-20 | 2026-07-21 |  |  |  | 2d | 324 |  |  |  |  | 99
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Development and Testing on STAGING Set Up | Not Started | 2026-08-11 | 2026-09-03 |  |  |  | 18d | [5 empty] | 67
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Integration set up and development at Zycus | Not Started | 2026-08-11 | 2026-08-17 |  |  |  | 5d | 319 |  |  |  |  | 80
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Integration development at Titan - as applicable | Not Started | 2026-08-11 | 2026-08-17 |  |  |  | 5d | 319 |  |  |  |  | 55
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Integration Unit Testing and Feedback Incorporation | Not Started | 2026-08-18 | 2026-08-19 |  |  |  | 2d | 328 |  |  |  |  | 55
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Systems Integration Testing | Not Started | 2026-08-20 | 2026-09-03 |  |  |  | 11d | [5 empty] | 67
| #UNPARSEABLE | 6 | Aftab Hashambhai | 6 |  |  | Green | SIT on STAGING Set Up | Not Started | 2026-08-20 | 2026-09-02 |  |  |  | 10d | 329 |  |  |  |  | 55
| #UNPARSEABLE | 6 | Aftab Hashambhai | 6 |  |  | Green | Sign off on SIT | Not Started | 2026-09-03 | 2026-09-03 |  |  |  | 1d | 331 |  |  |  |  | 55
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Integrations Punchout 1 | Not Started | 2026-07-13 | 2026-08-04 |  |  |  | 17d | [5 empty] | 89
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | eInvoice Integration | Not Started | 2026-07-13 | 2026-08-04 |  |  |  | 17d | [5 empty] | 89
| #UNPARSEABLE | 6 | Aftab Hashambhai | 6 |  |  | Green | Integration Design | Not Started | 2026-07-13 | 2026-07-16 |  |  |  | 4d | [5 empty] | 102
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | Questionnaire Sharing and Sample Files with Supplier | Not Started | 2026-07-13 | 2026-07-13 |  |  |  | 1d | 305 |  |  |  |  | 89
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | Supplier Registration on ZSN staging | Not Started | 2026-07-14 | 2026-07-16 |  |  |  | 3d | 336 |  |  |  |  | 89
| #UNPARSEABLE | 6 | Aftab Hashambhai | 6 |  |  | Green | Development and Testing on STAGING Set Up | Not Started | 2026-07-17 | 2026-08-04 |  |  |  | 13d | [5 empty] | 89
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | Punchout Setup and Connectivity testing | Not Started | 2026-07-17 | 2026-07-23 |  |  |  | 5d | 337 |  |  |  |  | 89
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | PO and Invoice Unit Testing | Not Started | 2026-07-24 | 2026-07-27 |  |  |  | 2d | 339 |  |  |  |  | 89
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | Zycus test case documentation | Not Started | 2026-07-28 | 2026-07-28 |  |  |  | 1d | 340 |  |  |  |  | 94
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | Systems Integration Testing | Not Started | 2026-07-28 | 2026-08-04 |  |  |  | 6d | [5 empty] | 89
| #UNPARSEABLE | 8 | Aftab Hashambhai | 8 |  |  | Green | SIT on STAGING Set Up | Not Started | 2026-07-28 | 2026-08-03 |  |  |  | 5d | 340 |  |  |  |  | 89
| #UNPARSEABLE | 8 | Aftab Hashambhai | 8 |  |  | Green | Sign off on SIT | Not Started | 2026-08-04 | 2026-08-04 |  |  |  | 1d | 343 |  |  |  |  | 89
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Integrations Punchout 2 | Not Started | 2026-07-13 | 2026-08-04 |  |  |  | 17d | [5 empty] | 89
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | eInvoice Integration | Not Started | 2026-07-13 | 2026-08-04 |  |  |  | 17d | [5 empty] | 89
| #UNPARSEABLE | 6 | Aftab Hashambhai | 6 |  |  | Green | Integration Design | Not Started | 2026-07-13 | 2026-07-16 |  |  |  | 4d | [5 empty] | 102
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | Questionnaire Sharing and Sample Files with Supplier | Not Started | 2026-07-13 | 2026-07-13 |  |  |  | 1d | 305 |  |  |  |  | 89
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | Supplier Registration on ZSN staging | Not Started | 2026-07-14 | 2026-07-16 |  |  |  | 3d | 348 |  |  |  |  | 89
| #UNPARSEABLE | 6 | Aftab Hashambhai | 6 |  |  | Green | Development and Testing on STAGING Set Up | Not Started | 2026-07-17 | 2026-08-04 |  |  |  | 13d | [5 empty] | 89
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | Punchout Setup and Connectivity testing | Not Started | 2026-07-17 | 2026-07-23 |  |  |  | 5d | 349 |  |  |  |  | 89
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | PO and Invoice Unit Testing | Not Started | 2026-07-24 | 2026-07-27 |  |  |  | 2d | 351 |  |  |  |  | 89
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | Zycus test case documentation | Not Started | 2026-07-28 | 2026-07-28 |  |  |  | 1d | 352 |  |  |  |  | 94
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | Systems Integration Testing | Not Started | 2026-07-28 | 2026-08-04 |  |  |  | 6d | [5 empty] | 89
| #UNPARSEABLE | 8 | Aftab Hashambhai | 8 |  |  | Green | SIT on STAGING Set Up | Not Started | 2026-07-28 | 2026-08-03 |  |  |  | 5d | 352 |  |  |  |  | 89
| #UNPARSEABLE | 8 | Aftab Hashambhai | 8 |  |  | Green | Sign off on SIT | Not Started | 2026-08-04 | 2026-08-04 |  |  |  | 1d | 355 |  |  |  |  | 89
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Integrations Punchout 3 | Not Started | 2026-07-13 | 2026-08-04 |  |  |  | 17d | [5 empty] | 89
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | eInvoice Integration | Not Started | 2026-07-13 | 2026-08-04 |  |  |  | 17d | [5 empty] | 89
| #UNPARSEABLE | 6 | Aftab Hashambhai | 6 |  |  | Green | Integration Design | Not Started | 2026-07-13 | 2026-07-16 |  |  |  | 4d | [5 empty] | 102
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | Questionnaire Sharing and Sample Files with Supplier | Not Started | 2026-07-13 | 2026-07-13 |  |  |  | 1d | 305 |  |  |  |  | 89
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | Supplier Registration on ZSN staging | Not Started | 2026-07-14 | 2026-07-16 |  |  |  | 3d | 360 |  |  |  |  | 89
| #UNPARSEABLE | 6 | Aftab Hashambhai | 6 |  |  | Green | Development and Testing on STAGING Set Up | Not Started | 2026-07-17 | 2026-08-04 |  |  |  | 13d | [5 empty] | 89
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | Punchout Setup and Connectivity testing | Not Started | 2026-07-17 | 2026-07-23 |  |  |  | 5d | 361 |  |  |  |  | 89
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | PO and Invoice Unit Testing | Not Started | 2026-07-24 | 2026-07-27 |  |  |  | 2d | 363 |  |  |  |  | 89
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | Zycus test case documentation | Not Started | 2026-07-28 | 2026-07-28 |  |  |  | 1d | 364 |  |  |  |  | 94
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | Systems Integration Testing | Not Started | 2026-07-28 | 2026-08-04 |  |  |  | 6d | [5 empty] | 89
| #UNPARSEABLE | 8 | Aftab Hashambhai | 8 |  |  | Green | SIT on STAGING Set Up | Not Started | 2026-07-28 | 2026-08-03 |  |  |  | 5d | 364 |  |  |  |  | 89
| #UNPARSEABLE | 8 | Aftab Hashambhai | 8 |  |  | Green | Sign off on SIT | Not Started | 2026-08-04 | 2026-08-04 |  |  |  | 1d | 367 |  |  |  |  | 89
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | eProc Config, Pre-UAT, Integration Design & Development and SIT | Not Started | 2026-07-13 | 2026-09-03 |  |  |  | 39d | [5 empty] | 67
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Functional Configuration Finalization on STAGING set Up | Not Started | 2026-07-14 | 2026-08-07 |  |  |  | 19d | [5 empty] | 86
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | User Roles configuration | Not Started | 2026-07-14 | 2026-07-15 |  |  |  | 2d | 296 |  |  |  |  | 88
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Admin settings configuration | Not Started | 2026-07-16 | 2026-07-17 |  |  |  | 2d | 371 |  |  |  |  | 88
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Configure Workflow | Not Started | 2026-07-20 | 2026-07-24 |  |  |  | 5d | 372 |  |  |  |  | 88
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Readiness for Pre-UAT | Not Started | 2026-07-27 | 2026-07-28 |  |  |  | 2d | 373 |  |  |  |  | 88
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Pre-UAT on STAGING | Not Started | 2026-07-27 | 2026-08-07 |  |  |  | 10d | [5 empty] | 86
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Pre-UAT - Provide End to end walkthrough of configured eProc to the Customer | Not Started | 2026-07-29 | 2026-07-31 |  |  |  | 3d | 374 |  |  |  |  | 88
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Pre-UAT for eProc Direct | Not Started | 2026-08-03 | 2026-08-05 |  |  |  | 3d | 376 |  |  |  |  | 88
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Provide feedback - if any for eProc Direct configuration | Not Started | 2026-07-27 | 2026-07-30 |  |  |  | 4d | [5 empty] | 55
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Zycus to incorporate feedback - as applicable and share final version of Implementation Approach Document [IAD] | Not Started | 2026-07-31 | 2026-08-06 |  |  |  | 5d | 378 |  |  |  |  | 55
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Sign off on Pre-UAT and final version of IAD | Not Started | 2026-08-07 | 2026-08-07 |  |  |  | 1d | 379 |  |  |  |  | 55
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | eProc Direct : Conclude Functional Configuration | Not Started | 2026-08-10 | 2026-08-10 |  |  |  | 1d | 380 |  |  |  |  | 55
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Integrations eProc Direct | Not Started | 2026-07-13 | 2026-09-03 |  |  |  | 39d | [5 empty] | 67
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | eProc Direct Integration | Not Started | 2026-07-13 | 2026-09-03 |  |  |  | 39d | [5 empty] | 67
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Integration Design | Not Started | 2026-07-13 | 2026-07-21 |  |  |  | 7d | [5 empty] | 99
| #UNPARSEABLE | 6 | Aftab Hashambhai | 6 |  |  | Green | Mapping activity for Integration | Not Started | 2026-07-13 | 2026-07-14 |  |  |  | 2d | 305 |  |  |  |  | 99
| #UNPARSEABLE | 6 | Aftab Hashambhai | 6 |  |  | Green | Share TDD for interface | Not Started | 2026-07-15 | 2026-07-15 |  |  |  | 1d | 385 |  |  |  |  | 99
| #UNPARSEABLE | 6 | Aftab Hashambhai | 6 |  |  | Green | Review of TDD and share feedback with Zycus | Not Started | 2026-07-16 | 2026-07-17 |  |  |  | 2d | 386 |  |  |  |  | 99
| #UNPARSEABLE | 6 | Aftab Hashambhai | 6 |  |  | Green | Sign off on TDD | Not Started | 2026-07-20 | 2026-07-21 |  |  |  | 2d | 387 |  |  |  |  | 99
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Development and Testing on STAGING Set Up | Not Started | 2026-08-11 | 2026-09-03 |  |  |  | 18d | [5 empty] | 67
| #UNPARSEABLE | 6 | Aftab Hashambhai | 6 |  |  | Green | Integration set up and development at Zycus | Not Started | 2026-08-11 | 2026-08-17 |  |  |  | 5d | 381 |  |  |  |  | 80
| #UNPARSEABLE | 6 | Aftab Hashambhai | 6 |  |  | Green | Integration development at Titan - as applicable | Not Started | 2026-08-11 | 2026-08-17 |  |  |  | 5d | 381 |  |  |  |  | 55
| #UNPARSEABLE | 6 | Aftab Hashambhai | 6 |  |  | Green | Integration Unit Testing and Feedback Incorporation | Not Started | 2026-08-18 | 2026-08-19 |  |  |  | 2d | 391 |  |  |  |  | 55
| #UNPARSEABLE | 6 | Aftab Hashambhai | 6 |  |  | Green | Systems Integration Testing | Not Started | 2026-08-20 | 2026-09-03 |  |  |  | 11d | [5 empty] | 67
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | SIT on STAGING Set Up | Not Started | 2026-08-20 | 2026-09-02 |  |  |  | 10d | 392 |  |  |  |  | 55
| #UNPARSEABLE | 7 | Aftab Hashambhai | 7 |  |  | Green | Sign off on SIT | Not Started | 2026-09-03 | 2026-09-03 |  |  |  | 1d | 394 |  |  |  |  | 55
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | eProc In-Direct Config, Pre-UAT, Integration Design & Development and SIT | Not Started | 2026-07-13 | 2026-09-03 |  |  |  | 39d | [5 empty] | 67
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Functional Configuration Finalization on STAGING set Up | Not Started | 2026-07-14 | 2026-08-07 |  |  |  | 19d | [5 empty] | 86
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | User Roles configuration | Not Started | 2026-07-14 | 2026-07-15 |  |  |  | 2d | 296 |  |  |  |  | 88
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Admin settings configuration | Not Started | 2026-07-16 | 2026-07-17 |  |  |  | 2d | 398 |  |  |  |  | 88
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Configure Workflow | Not Started | 2026-07-20 | 2026-07-24 |  |  |  | 5d | 399 |  |  |  |  | 88
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Readiness for Pre-UAT | Not Started | 2026-07-27 | 2026-07-28 |  |  |  | 2d | 400 |  |  |  |  | 88
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Pre-UAT on STAGING | Not Started | 2026-07-27 | 2026-08-07 |  |  |  | 10d | [5 empty] | 86
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Pre-UAT - Provide End to end walkthrough of configured eProc to the Customer | Not Started | 2026-07-29 | 2026-07-31 |  |  |  | 3d | 401 |  |  |  |  | 88
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | eProc Direct Pre-UAT | Not Started | 2026-08-03 | 2026-08-05 |  |  |  | 3d | 403 |  |  |  |  | 88
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Provide feedback - if any for eProc configuration | Not Started | 2026-07-27 | 2026-07-30 |  |  |  | 4d | [5 empty] | 55
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Zycus to incorporate feedback - as applicable and share final version of Implementation Approach Document [IAD] | Not Started | 2026-07-31 | 2026-08-06 |  |  |  | 5d | 405 |  |  |  |  | 55
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Sign off on Pre-UAT and final version of IAD | Not Started | 2026-08-07 | 2026-08-07 |  |  |  | 1d | 406 |  |  |  |  | 55
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | eProc Direct : Conclude Functional Configuration | Not Started | 2026-08-10 | 2026-08-10 |  |  |  | 1d | 407 |  |  |  |  | 55
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Integrations eInvoice | Not Started | 2026-07-13 | 2026-09-03 |  |  |  | 39d | [5 empty] | 67
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Integration Design | Not Started | 2026-07-13 | 2026-07-21 |  |  |  | 7d | [5 empty] | 99
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Mapping activity for Integration | Not Started | 2026-07-13 | 2026-07-14 |  |  |  | 2d | 305 |  |  |  |  | 99
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Share TDD for interface | Not Started | 2026-07-15 | 2026-07-15 |  |  |  | 1d | 411 |  |  |  |  | 99
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Review of TDD and share feedback with Zycus | Not Started | 2026-07-16 | 2026-07-17 |  |  |  | 2d | 412 |  |  |  |  | 99
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Sign off on TDD | Not Started | 2026-07-20 | 2026-07-21 |  |  |  | 2d | 413 |  |  |  |  | 99
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Development and Testing on STAGING Set Up | Not Started | 2026-08-11 | 2026-09-03 |  |  |  | 18d | [5 empty] | 67
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Integration set up and development at Zycus | Not Started | 2026-08-11 | 2026-08-17 |  |  |  | 5d | 408 |  |  |  |  | 80
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Integration development at Titan - as applicable | Not Started | 2026-08-11 | 2026-08-17 |  |  |  | 5d | 408 |  |  |  |  | 55
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Integration Unit Testing and Feedback Incorporation | Not Started | 2026-08-18 | 2026-08-19 |  |  |  | 2d | 417 |  |  |  |  | 55
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Systems Integration Testing | Not Started | 2026-08-20 | 2026-09-03 |  |  |  | 11d | [5 empty] | 67
| #UNPARSEABLE | 6 | Aftab Hashambhai | 6 |  |  | Green | SIT on STAGING Set Up | Not Started | 2026-08-20 | 2026-09-02 |  |  |  | 10d | 418 |  |  |  |  | 55
| #UNPARSEABLE | 6 | Aftab Hashambhai | 6 |  |  | Green | Sign off on SIT | Not Started | 2026-09-03 | 2026-09-03 |  |  |  | 1d | 420 |  |  |  |  | 55
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Masterdata Config, Pre-UAT, Integration Design & Development and SIT | Not Started | 2026-07-13 | 2026-09-03 |  |  |  | 39d | [5 empty] | 67
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Functional Configuration Finalization on STAGING set Up | Not Started | 2026-07-14 | 2026-08-07 |  |  |  | 19d | [5 empty] | 86
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | User Roles configuration | Not Started | 2026-07-14 | 2026-07-15 |  |  |  | 2d | 296 |  |  |  |  | 88
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Admin settings configuration | Not Started | 2026-07-16 | 2026-07-17 |  |  |  | 2d | 424 |  |  |  |  | 88
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Configure Workflow | Not Started | 2026-07-20 | 2026-07-24 |  |  |  | 5d | 425 |  |  |  |  | 88
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Readiness for Pre-UAT | Not Started | 2026-07-27 | 2026-07-28 |  |  |  | 2d | 426 |  |  |  |  | 88
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Pre-UAT on STAGING | Not Started | 2026-07-27 | 2026-08-07 |  |  |  | 10d | [5 empty] | 86
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Pre-UAT - Provide End to end walkthrough of configured eProc to the Customer | Not Started | 2026-07-29 | 2026-07-31 |  |  |  | 3d | 427 |  |  |  |  | 88
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Pre-UAT of Master Data | Not Started | 2026-08-03 | 2026-08-05 |  |  |  | 3d | 429 |  |  |  |  | 88
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Provide feedback - if any for masterdata configuration | Not Started | 2026-07-27 | 2026-07-30 |  |  |  | 4d | [5 empty] | 55
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Zycus to incorporate feedback - as applicable and share final version of Implementation Approach Document [IAD] | Not Started | 2026-07-31 | 2026-08-06 |  |  |  | 5d | 431 |  |  |  |  | 55
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Sign off on Pre-UAT and final version of IAD | Not Started | 2026-08-07 | 2026-08-07 |  |  |  | 1d | 432 |  |  |  |  | 55
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Master Data: Conclude Functional Configuration | Not Started | 2026-08-10 | 2026-08-10 |  |  |  | 1d | 433 |  |  |  |  | 55
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Integrations Master data | Not Started | 2026-07-13 | 2026-09-03 |  |  |  | 39d | [5 empty] | 67
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Integration Design | Not Started | 2026-07-13 | 2026-07-21 |  |  |  | 7d | [5 empty] | 99
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Mapping activity for Integration | Not Started | 2026-07-13 | 2026-07-14 |  |  |  | 2d | 305 |  |  |  |  | 99
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Share TDD for interface | Not Started | 2026-07-15 | 2026-07-15 |  |  |  | 1d | 437 |  |  |  |  | 99
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Review of TDD and share feedback with Zycus | Not Started | 2026-07-16 | 2026-07-17 |  |  |  | 2d | 438 |  |  |  |  | 99
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Sign off on TDD | Not Started | 2026-07-20 | 2026-07-21 |  |  |  | 2d | 439 |  |  |  |  | 99
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Development and Testing on STAGING Set Up | Not Started | 2026-08-11 | 2026-09-03 |  |  |  | 18d | [5 empty] | 67
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Integration set up and development at Zycus | Not Started | 2026-08-11 | 2026-08-17 |  |  |  | 5d | 434 |  |  |  |  | 80
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Integration development at Titan - as applicable | Not Started | 2026-08-11 | 2026-08-17 |  |  |  | 5d | 434 |  |  |  |  | 55
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Integration Unit Testing and Feedback Incorporation | Not Started | 2026-08-18 | 2026-08-19 |  |  |  | 2d | 443 |  |  |  |  | 55
| #UNPARSEABLE | 5 | Aftab Hashambhai | 5 |  |  | Green | Systems Integration Testing | Not Started | 2026-08-20 | 2026-09-03 |  |  |  | 11d | [5 empty] | 67
| #UNPARSEABLE | 6 | Aftab Hashambhai | 6 |  |  | Green | SIT on STAGING Set Up | Not Started | 2026-08-20 | 2026-09-02 |  |  |  | 10d | 444 |  |  |  |  | 55
| #UNPARSEABLE | 6 | Aftab Hashambhai | 6 |  |  | Green | Sign off on SIT | Not Started | 2026-09-03 | 2026-09-03 |  |  |  | 1d | 446 |  |  |  |  | 55
| #UNPARSEABLE | 1 | Aftab Hashambhai | 1 |  |  | Green | User Acceptance Testing (UAT) | Not Started | 2026-09-04 | 2026-10-20 | 0% |  |  | 33d | [5 empty] | 34
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Prepare for UAT | Not Started | 2026-09-04 | 2026-09-14 |  |  |  | 7d | [5 empty] | 60
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Prepare the UAT Approach | Not Started | 2026-09-04 | 2026-09-07 |  |  |  | 2d | 332, 395, 421, 447 |  |  |  |  | 55
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Finalize and agree on UAT Approach | Not Started | 2026-09-08 | 2026-09-09 |  |  |  | 2d | 450 |  |  |  |  | 63
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Provide users & roles on STAGING required for UAT | Not Started | 2026-09-08 | 2026-09-08 |  |  |  | 1d | 450 |  |  |  |  | 64
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Create users on STAGING set for UAT group | Not Started | 2026-09-08 | 2026-09-09 |  |  |  | 2d | 450 |  |  |  |  | 63
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Provide Standard Test Cases | Not Started | 2026-09-08 | 2026-09-10 |  |  |  | 3d | 450 |  |  |  |  | 55
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Finalize Test Cases | Not Started | 2026-09-11 | 2026-09-14 |  |  |  | 2d | 454 |  |  |  |  | 55
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Quality Reviews | Not Started | 2026-09-08 | 2026-09-11 |  |  |  | 4d | [5 empty] | 61
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Schedule for quality check | Not Started | 2026-09-08 | 2026-09-08 |  |  |  | 1d | 450 |  |  |  |  | 61
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Perform quality checks, PSRs as per quality checklist and submit to QC team | Not Started | 2026-09-09 | 2026-09-10 |  |  |  | 2d | 457 |  |  |  |  | 61
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Quality Check by Zycus QC team | Not Started | 2026-09-11 | 2026-09-11 |  |  |  | 1d | 458 |  |  |  |  | 61
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | End-to-End UAT | Not Started | 2026-09-15 | 2026-09-23 |  |  |  | 7d | [5 empty] | 53
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | UAT of End-to-end system - eProc & eInvoice | Not Started | 2026-09-15 | 2026-09-21 |  |  |  | 5d | 455 |  |  |  |  | 55
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Defect Analysis & UAT Feedback incorporation and share Test Closure Memo | Not Started | 2026-09-16 | 2026-09-22 |  |  |  | 5d | [5 empty] | 0 | TRUE
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Titan to provide sign off on Test Closure Memo | Not Started | 2026-09-23 | 2026-09-23 |  |  |  | 1d | 462 |  |  |  |  | 0 | TRUE
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Migration of Solution from UAT to PRODUCTION | Not Started | 2026-09-24 | 2026-10-09 | 0% |  |  | 12d | [5 empty] | 41 |  | 2026-07-20 | 2026-08-05 | -41d | [6 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Log ticket for PRODUCTION tenant creation (Starting with SSO sign off on STAGING) | Not Started | 2026-09-24 | 2026-09-24 | 0% |  |  | 1d | 463 |  |  |  |  | 45 |  | 2026-07-23 | 2026-07-23 | -41d |  |  |  | Zycus Product Specialist |  |  | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | iSupplier is PROD Ready with Supplier Bulk upload on PRODUCTION | Not Started | 2026-09-25 | 2026-09-25 | 0% |  |  | 1d | 465 |  |  |  |  | 45 |  | 2026-07-28 | 2026-07-28 | -41d |  |  |  | Zycus Consultant, Zycus Product Specialist |  |  | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | ZSN & P2P configuration for catalog uploads by Titan/Supplier | Not Started | 2026-09-28 | 2026-09-30 | 0% |  |  | 3d | 466 |  |  |  |  | 48 |  | 2026-07-24 | 2026-07-28 | -41d |  |  |  | Zycus Product Specialist |  |  | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Titan to provide refreshed Master data for PRODUCTION | Not Started | 2026-09-24 | 2026-09-28 | 0% |  |  | 3d | 463 |  |  |  |  | 50 |  | 2026-07-20 | 2026-07-22 | -41d |  |  |  | Titan Project Team |  |  | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Zycus validation and data iterations | Not Started | 2026-09-28 | 2026-09-30 | 0% |  |  | 3d | 466 |  |  |  |  | 45 |  | 2026-07-23 | 2026-07-27 | -41d |  |  |  | Zycus Product Specialist |  |  | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Titan to move integration code to PRODUCTION environment | Not Started | 2026-10-01 | 2026-10-05 | 0% |  |  | 3d | 469 |  |  |  |  | 45 |  | 2026-07-23 | 2026-07-27 | -41d |  |  |  | Titan Project Team |  |  | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Setup PRODUCTION environment (master data) - Zycus | Not Started | 2026-09-24 | 2026-09-30 | 0% |  |  | 5d | 463 |  |  |  |  | 48 |  | 2026-07-28 | 2026-08-03 | -41d |  |  |  | Zycus Product Specialist |  |  | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Setup PRODUCTION environment (configuration) - Zycus | Not Started | 2026-09-24 | 2026-09-30 | 0% |  |  | 5d | 463 |  |  |  |  | 48 |  | 2026-07-28 | 2026-08-03 | -41d |  |  |  | Zycus Product Specialist |  |  | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Setup PRODUCTION environment (Integration) - Zycus | Not Started | 2026-09-24 | 2026-09-30 | 0% |  |  | 5d | 463 |  |  |  |  | 0 | TRUE | 2026-07-24 | 2026-07-30 | -41d |  |  |  | Zycus Product Specialist |  |  | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Quality Check | Not Started | 2026-10-01 | 2026-10-09 | 0% |  |  | 7d | [5 empty] | 41 |  | 2026-07-28 | 2026-08-05 | -41d | [6 empty] | Yellow
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Schedule for quality check | Not Started | 2026-10-01 | 2026-10-01 | 0% |  |  | 1d | 473 |  |  |  |  | 0 | TRUE | 2026-07-28 | 2026-07-28 | -41d |  |  |  | Zycus Product Specialist |  |  | Yellow
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Perform quality checks, PSRs as per quality checklist and submit to QC team | Not Started | 2026-10-02 | 2026-10-08 | 0% |  |  | 5d | 475 |  |  |  |  | 0 | TRUE | 2026-08-04 | 2026-08-04 | -41d |  |  |  | Zycus Product Specialist |  |  | Yellow
| #UNPARSEABLE | 4 | Aftab Hashambhai | 4 |  |  | Green | Quality Check by Zycus QC team | Not Started | 2026-10-09 | 2026-10-09 | 0% |  |  | 1d | 476 |  |  |  |  | 0 | TRUE | 2026-08-05 | 2026-08-05 | -41d |  |  |  | Zycus Quality Team |  |  | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Training | Not Started | 2026-10-12 | 2026-10-20 | 0% |  |  | 7d | [5 empty] | 34 |  | 2026-08-03 | 2026-08-07 | -38d | [6 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | eProc Training (Train the Trainer) | Not Started | 2026-10-12 | 2026-10-15 | 0% |  |  | 4d | 477 |  |  |  |  | 34 |  | 2026-08-03 | 2026-08-06 | -36d |  |  |  | Titan Project Manager, Titan Project Team, Zycus University Trainer |  |  | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | eInvoice Training (Train the Trainer) | Not Started | 2026-10-16 | 2026-10-19 | 0% |  |  | 2d | 479 |  |  |  |  | 34 |  | 2026-08-03 | 2026-08-04 | -40d |  |  |  | Titan Project Manager, Titan Project Team, Zycus University Trainer |  |  | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Admin Training | Not Started | 2026-10-20 | 2026-10-20 | 0% |  |  | 1d | 480 |  |  |  |  | 34 |  | 2026-08-07 | 2026-08-07 | -38d |  |  |  | Titan Project Manager, Titan Project Team, Zycus University Trainer |  |  | Yellow
| #UNPARSEABLE | 1 | Aftab Hashambhai | 1 |  |  | Green | P2P Cutover | Not Started | 2026-10-12 | 2026-12-07 | 0% |  |  | 41d | [5 empty] | 0 |  | 2026-07-13 | 2026-08-07 | -62d | [6 empty] | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | First Go-Live communication to all suppliers | Not Started | 2026-10-12 | 2026-10-13 | 0% |  |  | 2d | 477 |  |  |  |  | 0 | TRUE | 2026-07-13 | 2026-07-13 | -59d |  |  |  | Titan Project Team |  |  | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Share updated P2P user list | Not Started | 2026-10-12 | 2026-10-13 | 0% |  |  | 2d | 477 |  |  |  |  | 39 |  | 2026-07-27 | 2026-07-27 | -51d |  |  |  | Titan Project Team |  |  | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Second Go-Live communication to all suppliers | Not Started | 2026-10-14 | 2026-10-15 | 0% |  |  | 2d | 483 |  |  |  |  | 0 | TRUE | 2026-07-27 | 2026-07-27 | -53d |  |  |  | Titan Project Team |  |  | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Close all requisitions/PO/invoices in existing system | Not Started | 2026-10-16 | 2026-10-22 | 0% |  |  | 5d | 485 |  |  |  |  | 0 | TRUE | 2026-08-06 | 2026-08-06 | -50d |  |  |  | Titan Project Team |  |  | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Supplier/Titan to load catalogues on ZSN | Not Started | 2026-10-23 | 2026-10-29 | 0% |  |  | 5d | 486 |  |  |  |  | 0 | TRUE | 2026-08-06 | 2026-08-07 | -54d |  |  |  | Titan Project Team |  |  | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Load delta master data via integration | Not Started | 2026-10-30 | 2026-11-05 | 0% |  |  | 5d | 487 |  |  |  |  | 0 | TRUE | 2026-07-31 | 2026-08-03 | -63d |  |  |  | Titan Integration Team |  |  | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Titan Quality Check | Not Started | 2026-11-06 | 2026-11-06 | 0% |  |  | 1d | 488 |  |  |  |  | 0 | TRUE | 2026-08-05 | 2026-08-05 | -63d |  |  |  | Titan Project Team |  |  | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Go Live | Not Started | 2026-11-09 | 2026-11-09 | 0% |  |  | 1d | [5 empty] | 20 |  | 2026-08-10 | 2026-08-10 | -61d | [6 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Release P2P to all users requiring access for Pilot launch | Not Started | 2026-11-09 | 2026-11-09 | 0% |  |  | 1d | 489 |  |  |  |  | 0 | TRUE | 2026-08-10 | 2026-08-10 | -61d |  |  |  | Titan Project Manager, Titan Project Team, Zycus Product Specialist |  |  | Yellow
| #UNPARSEABLE | 2 | Aftab Hashambhai | 2 |  |  | Green | Hypercare | Not Started | 2026-11-10 | 2026-12-07 |  |  |  | 20d | [5 empty] | 0 | [10 empty] | Yellow
| #UNPARSEABLE | 3 | Aftab Hashambhai | 3 |  |  | Green | Hypercare Support | Not Started | 2026-11-10 | 2026-12-07 |  |  |  | 20d | 491 |  |  |  |  | 0 | TRUE

## Comments
Row 292 | As per scheduled agenda we have coverd all sessions | Sarika Arthmwar | 06/26/26 2:25 PM
Row 292 | Due to parallel phase 1 activities onsite workshop dates are impacted | Sarika Arthmwar | 05/18/26 7:31 AM
Row 294 | OTK to provde Sample for processing further with Design conclusion however the complete data will be providd by or before July 10 | Sarika Arthmwar | 06/26/26 2:36 PM
Row 299 | JDE mapping is pending only | Sarika Arthmwar | 06/26/26 2:39 PM
Row 301 | JDE field mapping remain to complete for PO outbound & GR Inbound @vinayaka.soratoor@zycus.com | Sarika Arthmwar | 06/26/26 2:40 PM
Row 385 | @aftab.hashambhai@zycus.com Need meeting on calendar for this | Vinayaka Soratoor | 06/23/26 9:29 AM
Row 391 | @aftab.hashambhai@zycus.com PH name need to be changed | Vinayaka Soratoor | 06/23/26 9:30 AM
Row 411 | @aftab.hashambhai@zycus.com Need to have these on calendar, as a outcome of workshop mapping will be complete, OTK will have time till this date to review and make any changes | Vinayaka Soratoor | 06/23/26 9:25 AM
Row 435 | @aftab.hashambhai@zycus.com eInvoice section is repeating | Vinayaka Soratoor | 06/23/26 9:27 AM

## Summary
Project Name
Project Manager | Aftab Hashambhai
Project Start Date | 2025-12-05
Project End Date | 2026-12-07
Not Started | 194
In Progress | 15
Completed | 255
On Hold | 3
At Risk | High
Project Stage | Configuration and Build phase
% Complete | 71%
Schedule Health | Green
Today's Date | 2026-07-02
Target Start Date | #UNPARSEABLE
Target End Date | #UNPARSEABLE
Schedule Delta | #UNPARSEABLE
Duration | 262
Target Dates Variance | #UNPARSEABLE
Schedule Variance | #UNPARSEABLE
Project Status | In Progress