## Slide 1
Monthly Portfolio Health Synthesis
Cross-project RAG status, synthesized from live project-plan data
Generated 2026-07-10 00:22 | 2 project(s)
Report period: 2026-06-05 to 2026-06-26 (up to 4 weekly runs recorded so far)

## Slide 2
Portfolio Health Overview
Traffic-light status across all tracked projects
Zycus - Titan S2P Implementation
Composite score: 65.0 | Confidence: Medium
Red
2 red signal(s)
Zycus - UniSan S2P Implementation
Composite score: 89.7 | Confidence: High
Green
no red signals

## Slide 3
Emerging Risks
Signals currently pulling status down (single snapshot — see Trend Analysis)
Portfolio pattern: Milestone Health is a shared weak spot across all 2 tracked project(s). • No project in this portfolio has budget/cost tracking data in its source plan.
Zycus - Titan S2P Implementation
Red
●
9 of its 14 milestones are delayed or missed, including Configuration and Build phase and UAT
●
One blocker ("Supplier Notification template") has been open for 92 days
●
Stakeholder comments read mostly cautious or mixed
Zycus - UniSan S2P Implementation
Green
●
1 of its 39 milestones is delayed or missed, including Training Phase I
Note: 4 weekly snapshots recorded for at least one project — see Trend Analysis for the real composite-score trend across them.

## Slide 4
Milestone Tracker
Delayed or missed milestones by project
Zycus - Titan S2P Implementation
Red
9/14 milestones delayed or missed
Configuration and Build phase, UAT, Train The Trainer, Production & Cutover, Go-Live & Support intro, Hyper Care(Measure and Adoption) Solution...
Zycus - UniSan S2P Implementation
Amber
1/39 milestones delayed or missed
Training Phase I

## Slide 5
Budget Summary
No cost/budget column exists in either source project plan. Budget burn cannot be measured this period — figures below are not fabricated.
Zycus - Titan S2P Implementation
N/A
Signal dropped — no budget data in source; weight redistributed to the other four signals
Zycus - UniSan S2P Implementation
N/A
Signal dropped — no budget data in source; weight redistributed to the other four signals

## Slide 6
Trend Analysis
Composite RAG Score Over Time (real weekly runs, not modeled)
Zycus - Titan S2P Implementation
Red
Jun 05 · 65
Red
Jun 12 · 65
Red
Jun 19 · 65
Red
Jun 26 · 65
Zycus - UniSan S2P Implementation
Green
Jun 05 · 90
Green
Jun 12 · 90
Green
Jun 19 · 90
Green
Jun 26 · 90
What's ALSO real: Stakeholder Sentiment Over Time
Comment timestamps are real, dated facts — re-scoring sentiment using only comments that existed by each past week is measuring history, not modeling it.
Zycus - Titan S2P Implementation
Amber
3 weeks ago
Amber
2 weeks ago
Amber
1 week ago
Amber
This week
Zycus - UniSan S2P Implementation
N/A
3 weeks ago
N/A
2 weeks ago
N/A
1 week ago
N/A
This week

## Slide 7
Recommendations
Generated for a VP audience from this month's portfolio data
1
Implement enhanced milestone tracking and monitoring mechanisms across all projects, particularly focusing on Zycus - Titan S2P Implementation due to its high number of delayed or missed milestones.
2
Develop a standardized budget/cost tracking framework applicable to the entire portfolio, starting with projects like Zycus - Titan S2P Implementation where financial oversight is currently lacking.
3
Initiate comprehensive stakeholder sentiment analysis for all projects, leveraging insights from Zycus - UniSan S2P Implementation as a model to improve engagement and address concerns across the board.