## Slide 1
Zycus - Titan S2P Implementation
Monthly Project Health Summary
Generated 2026-07-10 00:23
Report period: 2026-06-05 to 2026-06-26 (up to 4 weekly runs recorded so far)

## Slide 2
Status at a Glance
Red
This project needs attention now — one or more areas are seriously behind.
Confidence in this read: Medium — some expected data was missing, so treat this read with a little caution.
Escalation note: Milestones and Blockers are both seriously behind this month. When two or more areas are this critical, the status is capped at Red regardless of the composite score.
Zycus - Titan S2P Implementation is Red this week. In plain terms: 9 of its 14 milestones are delayed or missed, including Configuration and Build phase and UAT; one blocker ("Supplier Notification template") has been open for 92 days; and stakeholder comments read mostly cautious or mixed. Data confidence for this read is medium.

## Slide 3
What's Driving This Status
Every area we measured, in plain terms
Schedule
Green
Only about 2.0% of tasks are behind schedule, which is a healthy range
Budget
N/A
Not enough data for this project — left out of the score.
Milestones
Red
9 of its 14 milestones are delayed or missed, including Configuration and Build phase and UAT
Blockers
Red
One blocker ("Supplier Notification template") has been open for 92 days
Team Feedback
Amber
Stakeholder comments read mostly cautious or mixed
Key Deadlines
Green
No tasks on the tightest part of the schedule are currently late

## Slide 4
Milestone Tracker
Delayed or missed milestones by project
Zycus - Titan S2P Implementation
Red
9/14 milestones delayed or missed
Configuration and Build phase, UAT, Train The Trainer, Production & Cutover, Go-Live & Support intro, Hyper Care(Measure and Adoption) Solution...

## Slide 5
Trend Analysis
Composite RAG Score Over Time (real weekly runs, not modeled)
Zycus - Titan S2P Implementation
Red
Jun 05 · 65
Red
Jun 12 · 65
Red
Jun 19 · 65
Red
Jun 26 · 65
What's ALSO real: Stakeholder Sentiment Over Time
Comment timestamps are real, dated facts — re-scoring sentiment using only comments that existed by each past week is measuring history, not modeling it.
Zycus - Titan S2P Implementation
Amber
3 weeks ago
Amber
2 weeks ago
Amber
1 week ago
Amber
This week

## Slide 6
Recommendations
Generated for a VP audience from this month's project data
1
Conduct an immediate review and reassessment of the current milestone timelines to identify critical path adjustments.
2
Initiate stakeholder engagement sessions to understand concerns and gather insights for improving confidence in project delivery.
3
Prioritize resolving open blockers, starting with the 'Supplier Notification template' issue due to its prolonged status.
4
Implement a more robust change management process to better handle configuration and build phase challenges.
5
Enhance communication strategies to ensure transparency and maintain stakeholder trust throughout project progression.